## TIP Projects - VDOT Data
mpo | src | record | upc | system | jurisdiction | scope | pe_expend | rw_expend | cn_expend | to_expend | last_expend | title and/or desription | from | to | route | streename | start mile | end mile | length | units | PE Cost Estimate | RW Cost Estimate | CN Cost Estimate | Total Cost Estimate | stip_cost | pe_start | pe_end | rw_start | rw_end | cn_start | cn_end | total allocation | pe_plan_oblg | rw_plan_oblg | cn_plan_oblg | planned obligation | actual_pe_obl | actual_rw_obl | actual_cn_obl | actual obligation | oversight | admin_by | regsig
Hampton Roads |  |  | T30082 | Urban | Virginia Beach | Facilities for Pedestrians and Bicyclists | [5 empty] | Install 3.2 miles of a 14-foot wide asphalt path from Newtown Road to Constitution Drive. Includes a pedestrian bridge over Indpendence Boulevard. First phase of a 12-mile trail project located within the previous Norfolk Southernn Railroad right-of-way. | Newtown Road (city limit between VB and NO) | Constitution Drive |  | N/A |  |  |  |  | 1647000 | 2637000 | 30153538 | 34437538 |  | 2024-08-01 | 2026-02-28 | 2026-03-01 | 2026-09-30 | 2026-10-01 | 2029-03-31 | 34437538 | [8 empty] | NFO | Locality | No
Hampton Roads | stip | program | T29917 | Miscellaneous | Statewide | Other | [5 empty] | TRANSFORMING RAIL IN VIRGINIA / VPRA | DC Rte 47, and Rte 51 | Newport News, Richmond | 9999 |  |  |  | 0.0000 | MI | 117037149 | 0 | 0 | 117037149 | 117574889 | 2024-08-01: 2022-04-26; 2026-02-28: 2027-04-26 | 117037149 | 0 | 0 | 0 | 0 | [5 empty] | VPRA | Yes
Hampton Roads |  |  | T24867 | Primary | Chesapeake Bay-Bridge Tunnel District | New Construction | 0 | 0 | 0 | 0 |  | Chesapeake Bay Bridge and Tunnel Parallel Chesapeake Tunnel (PE and RW Only) | Parallel Entrance of Chesapeake Tunnel | Parallel Exit of Chesapeake Tunnel | 13 |  |  |  | 1.8 | MI | 4800000 | 0 | 0 | 4800000 | [7 empty] | 4800000 | [9 empty] | CBBTD | Yes
Hampton Roads | stip | program | T24778 | Interstate | Multi-jurisdictional: Hampton Roads MPO | Other | [5 empty] | HREL Toll Integration - Systems Integrator - HRTAC |  |  | 9999 | I64 |  |  |  |  | 5873452 | 0 | 33282898 | 39156350 | 39156350 | 2021-04-01 | 2022-05-10 |  |  | 2022-05-10 | 2025-12-31 | 39156351 | 0 | 0 | 0 | 0 | [5 empty] | VDOT | Yes
Hampton Roads |  |  | T22709 | Public Transportation | Hampton Roads Transit | Transit | 0 | 0 | 0 | 0 |  | Victoria Blvd Facility Upgrades - Phase 2 |  |  |  | Victoria Blvd |  |  |  |  | 10100000 | 0 | 897100 | 10997100 |  | 2024-10-01 | 2027-03-31 |  |  | 2027-01-01 | 2029-03-31 | 12385763 | [8 empty] | FO | HRT-DRPT | No
Hampton Roads |  |  | T19468 | Public Transportation | Williamsburg Area Transit Authority | Transit | 0 | 0 | 0 | 0 |  | Expansion of Bus Shelters | [8 empty] | 72000 | 18000 | 144000 | 234000 |  | 2025-10-15 | 2025-10-15 | 2024-10-15 | 2025-10-15 | 2025-01-15 | 2027-01-15 | 234000 | [8 empty] | FO | WATA-DRPT | No
Hampton Roads |  |  | T17898 | Public Transportation | Williamsburg Area Transit Authority | Transit | 0 | 0 | 0 | 0 |  | WATA Transfer Station Hub |  |  |  | Old Mooretown Road |  |  |  |  | 1001041 | 0 | 1498959 | 2500000 |  | 2023-05-04 | 2024-10-01 |  |  | 2024-12-15 | 2026-12-30 | 2500000 | [8 empty] | FO | WATA-DRPT | No
Hampton Roads |  |  | T16054 | Public Transportation | Hampton Roads Transit | Transit | 0 | 0 | 0 | 0 |  | Transit Bus Replacement - Purchase replacement 29, 35, and 40-foot transit buses | [8 empty] | 28347509 | 0 | 0 | 28347509 |  | 2024-08-01: 2020-10-15; 2026-02-28: 2028-06-30 | 35520505 | [8 empty] | FO | HRT-DRPT | No
Hampton Roads |  |  | T15554 | Primary | Chesapeake Bay-Bridge Tunnel District | New Construction | 0 | 0 | 0 | 0 |  | Chesapeake Bay Bridge and Tunnel Parallel Thimble Shoal Tunnel | Parallel Entrance of Thimble Shoal Tunnel | Parallel Exit of Thimble Shoal | 13 |  |  |  | 3.13 | MI | 20630720 | 0 | 904160004 | 924160004 |  | 2013-05-01 | 2016-07-01 |  |  | 2016-07-01 | 2027-12-01 | 924160004 | [9 empty] | CBBTD | Yes
Hampton Roads |  |  | T14104 | Public Transportation | Hampton Roads Transit | Transit | 0 | 0 | 0 | 0 |  | goCommute - Ongoing Regional Traffic Demand Management (TDM) Program | [8 empty] | 7892141 | 0 | 0 | 7892141 |  | 2024-08-01: 2022-07-01; 2026-02-28: 2029-09-30 | 13892141 | [8 empty] | FO | HRT-DRPT | No
Hampton Roads |  |  | T11932 | Public Transportation | Williamsburg Area Transit Authority | Transit | 0 | 0 | 0 | 0 |  | WATA Administration and Operations Facility | [8 empty] | 486640 | 1946500 | 10358581 | 12791721 |  | 2020-11-20 | 2024-12-30 | 2018-07-27 | 2020-12-31 | 2024-12-15 | 2026-12-30 | 12791721 | [8 empty] | FO | WATA-DRPT | No
Hampton Roads |  |  | T11780 | Public Transportation | Williamsburg Area Transit Authority | Transit | 0 | 0 | 0 | 0 |  | Purchase Replacement Transit Buses | [8 empty] | 4937222 | 0 | 0 | 4937222 |  | 2024-08-01: 2024-10-15; 2026-02-28: 2027-01-15 | 4937222 | [8 empty] | FO | WATA-DRPT | No
Hampton Roads |  |  | T11779 | Public Transportation | Williamsburg Area Transit Authority | Transit | 0 | 0 | 0 | 0 |  | Purchase Replacement Compressed Natural Gas (CNG) Buses | [8 empty] | 3073000 | 0 | 0 | 3073000 |  | 2024-08-01: 2024-11-15; 2026-02-28: 2027-01-15 | 3073000 | [8 empty] | FO | WATA-DRPT | No
Hampton Roads | stip | project | 12546 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 9379445 | 35029393 | 41327253 | 85736092 | 2026-01-13 | #HB2.FY17 RTE 58 - WIDEN TO 6-LANE DIVIDED FACILITY | 0.28 Miles WEST OF FIRST COLONIAL ROAD | 0.32 Miles EAST OF BIRDNECK ROAD | 0058 | LASKIN ROAD | 506.76 | 508.91 | 2.1000 | MI | 9379445 | 38215976 | 42573501 | 90168922 | 90168922 | 1993-04-12 | 2002-02-21 | 2002-02-21 | 2019-01-22 | 2019-01-22 | 2025-07-31 | 93148333 | 0 | 0 | 0 | 0 | 0 | 34901300 | 19996302.14 | 54897602.14 | NFO | VDOT | Yes
Hampton Roads | stip | project | 13427 | Urban | Poquoson | Reconstruction W/ Added Capacity | 3130932 | 3878543 | 2962385 | 9971860 | 2026-01-09 | RTE 172 - CITY OF POQUOSON - PHASE I | Poquoson City Limits | 0.927 Mi. North of Poquoson City Limits | 0172 | WYTHE CREEK RD. | 3.87 | 2.91 | 0.9270 | MI | 3130932 | 4057600 | 11247828 | 18436360 | 18436360 | 2001-09-12 | 2017-02-03 | 2017-02-03 | 2023-11-09 | 2023-11-09 | 2027-11-05 | 18436360 | 0 | 0 | 0 | 0 | 2481170.62 | 0 | 5399474 | 7880644.62 | NFO | VDOT | Yes
Hampton Roads | stip | project | 15827 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 3975491 | 26981104 | 38454528 | 69411123 | 2025-06-03 | HOLLAND ROAD - UPGRADE TO 4 LANES | 0.207 MILE NORTH OF DAM NECK ROAD | 0.152 MILE SOUTH OF NIMMO PARKWAY | U000 | HOLLAND ROAD | 0 | 6.86 | 2.7200 | MI | 3975491 | 27296848 | 37000000 | 68272339 | 68272339 | 1998-06-30 17:00 | 2006-03-10 17:00 | 2006-03-10 17:00 | 2014-06-03 17:00 | 2014-06-03 17:00 | 2018-12-13 | 68272339 | 0 | 0 | 0 | 0 | 2944000 | 19669548 | 0 | 22613548 | NFO | VDOT | Yes
Hampton Roads | stip | budget | 15828 | Urban | Virginia Beach | New Construction Roadway | 3996645 | 2570125 | 6868720 | 13435491 | 2026-01-06 | Elbow Road Phase 2B | Margaret Drive/Meadow Crest Way | Chesapeake City Line | U000 | ELBOW ROAD | 0.12 | 1.44 | 1.3000 | MI | 7793000 | 5500000 | 62683685 | 75976685 | 75976685 | 1996-03-26 | 2006-03-10 | 2006-03-10 | 2023-08-23 | 2023-08-23 | 2026-09-21 | 75976685 | 0 | 0 | 0 | 0 | 5495199 | 4439362 | 9481864 | 19416425 | NFO | Locally | Yes
Hampton Roads | stip | budget | 15829 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 4567946 | 4242157 | 0 | 8810103 | 2026-01-06 | #HB2.FY17 INDIAN RIVER ROAD Ph 7A | LYNNHAVEN PARKWAY | ELBOW ROAD | U000 | INDIAN RIVER ROAD | 9.33 | 11.53 | 2.2000 | KM | 6465000 | 26338000 | 63154547 | 95957547 | 95957547 | 1996-03-26 | 2006-03-10 | 2006-03-10 | 2031-07-01 | 2031-07-01 | 2034-05-02 | 56103000 | 0 | 0 | 0 | 0 | 3069282 | 0 | 0 | 3069282 | NFO | Locally | Yes
Hampton Roads | stip | project | 16314 | Secondary | York County | Reconstruction W/O Added Capacity | 800331 | 1387500 | 4369053 | 6556885 | 2026-01-06 | Penniman Rd/Government Rd/ROADWAY IMPROVEMENTS | 0.010 Mi. West of Int. Rte. 723 (Fillmore Dr) | 0.045 Mi. East of Int. Rte. 705 (Alexander Lee Pkwy) | 0641 | PENNIMAN ROAD | 1.5 | 1.8 | 0.3080 | MI | 800331 | 1416130 | 4774931 | 6991392 | 6991392 | 2000-08-24 | 2020-03-18 | 2020-03-18 | 2023-10-10 | 2023-10-10 | 2025-07-22 | 7448443 | 0 | 0 | 0 | 0 | 434266 | 1262195 | 1991151 | 3687612 | NFO | VDOT | No
Hampton Roads | stip | project | 17630 | Interstate | Virginia Beach | Reconstruction W/ Added Capacity | 13844282 | 0 | 58230702 | 72074984 | 2025-06-10 | #SMART18 - I-264/WITCHDUCK RD INTERCHANGE & RAMP EXTENSION | 0.383 MILE EAST OF WBL I-64 | 0.472 MILE EAST OF WITCHDUCK RD | 0264 |  | 13.22 | 15.61 | 2.3000 | MI | 13844282 | 0 | 58230702 | 72074984 | 70567360 | 2000-12-08 | 2015-04-30 | 2015-04-30 | 2017-07-25 | 2017-07-25 | 2022-11-12 | 72111494 | 0 | 0 | 0 | 0 | 11969572 | 0 | 33454807 | 45424379 | FO | VDOT | Yes
Hampton Roads | stip | project | 17633 | Primary | James City County | Facilities For Pedestrians And Bicycles | 908401 | 1252388 | 2456051 | 4616839 | 2025-12-08 | Sidewalk and Bikeway on Rte 60 from Croaker to Old Church Rd | Richmond Rd and Croaker Rd | Richmond Rd and Old Church Road | BW00 | Richmond Road | 231.48 | 231.84 | 0.3300 | MI | 908401 | 1252388 | 2456051 | 4616840 | 4325089 | 1997-09-30 | 2020-09-17 | 2020-09-17 | 2022-08-09 | 2022-08-09 | 2024-10-31 | 3767028 | 0 | 0 | 0 | 0 | 711425.32 | 894359 | 1333412 | 2939196.32 | NFO | VDOT | No
Hampton Roads | stip | project | 59175 | Urban | Norfolk | New Construction Roadway | 3873204 | 39804 | 14592 | 3927601 | 2026-01-06 | AIR TERMINAL INTERCHANGE - INTERMODAL CONNECTOR - WESTERN | Seabee Rd Int. Sta 30+07 | I-564 IMC Median. Sta 47+50 | R000 |  | 1.52 | 2.27 | 0.3301 | MI | 4138000 | 326977 | 9576500 | 14041477 | 18410636 | 2014-09-08 | 2025-02-07 | 2025-02-07 | 2025-07-08 | 2025-07-08 | 2025-11-14 | 14041477 | 0 | 0 | 0 | 0 | 1362790.12 | 0 | 0 | 1362790.12 | FO | VDOT | Yes
Hampton Roads | stip | budget | 69050 | Urban | Suffolk | Reconstruction W/O Added Capacity | 1648551 | 8268898 | 14099739 | 24017188 | 2026-01-06 | #HB2.FY17 Bridge Rd & Shoulders Hill Rd Intersection Imps | .4 Miles W. of Rte 626 & .35 Miles S. of Rte 17 | .4 Miles E. of Rte 626 & .035 Miles N. of Rte 17 | 0626 | Bridge Rd (Rte 17) at Shoulders HIll Rd (Rte 626) | 35 | 37 | 0.2000 | MI | 1824916 | 10239534 | 23369501 | 35433951 | 35395697 | 2003-09-24 | 2019-08-20 | 2019-08-20 | 2022-04-14 | 2022-04-14 | 2025-10-10 | 36037470 | 0 | 0 | 0 | 0 | 1812793.97 | 10239587 | 8866060 | 20918440.97 | NFO | Locally | No
Hampton Roads | stip | project | 97715 | Urban | Hampton | Reconstruction W/ Added Capacity | 3559365 | 2474333 | 33034469 | 39068167 | 2026-01-13 | Wythe Creek Road - Widen to 3 Lanes | 0.965 Mi. S. of Hampton City Limits | Hampton City Limits | 0172 | Wythe Creek Road | 1.89 | 2.91 | 0.9650 | MI | 3559365 | 2474333 | 54066327 | 60100025 | 60100025 | 2011-02-28 | 2016-11-15 | 2016-11-15 | 2023-11-09 | 2023-11-09 | 2027-11-05 | 60131449 | 0 | 0 | 0 | 0 | 2847295.86 | 1979393.53 | 42434388.61 | 47261078 | NFO | VDOT | Yes
Hampton Roads | stip | project | 100920 | Secondary | James City County | Reconstruction W/ Added Capacity | 1928983 | 2553088 | 14419249 | 18901320 | 2026-01-12 | Croaker Road - Four Lane Widening From Library to Rte 60 | 0.512 Miles South of Rose Lane | 0.233 Miles North of Rose Lane | 0607 | CROAKER ROAD | 0.145 | 0.89 | 0.7450 | MI | 1928983 | 3443000 | 23268073 | 28640056 | 28652469 | 2012-02-08 | 2020-11-10 | 2020-11-10 | 2023-09-12 | 2023-09-12 | 2027-12-21 | 28629361 | 0 | 0 | 0 | 0 | 1476800 | 2754400 | 14260498 | 18491698 | NFO | VDOT | Yes
Hampton Roads | stip | budget | 100937 | Urban | Suffolk | Reconstruction W/ Added Capacity | 239808 | 16844862 | 39425320 | 56509990 | 2026-01-06 | #HB2.FY17 Route 58/ Holland Road Corridor Improvements | Rte 58/13/32 bypass | .7 miles west of Manning Bridge Road | 0058 | Holland Road | 466.73 | 463.64 | 3.1000 | MI | 3695424 | 34134544 | 45951216 | 83781184 | 83781184 | 2012-05-02 | 2015-07-20 | 2015-07-20 | 2020-09-30 | 2020-09-30 | 2025-02-10 | 83781184 | 0 | 0 | 8059225 | 8059225 | 28000 | 0 | 0 | 28000 | FO | Locally | No
Hampton Roads | stip | budget | 102951 | Primary | Isle of Wight County | Facilities For Pedestrians And Bicycles | 167224 | 0 | 888623 | 1055847 | 2026-01-06 | Main Street Pedestrian Improvements | Route 10 | Route 10 (Intersection) | 0258 | Main Street | 0.64 | 0.64 |  |  | 167224 | 0 | 1762720 | 1929944 | 1850880 | 2019-01-24 | 2023-01-06 | 2023-01-06 | 2024-08-12 | 2024-08-12 | 2025-10-23 | 1929944 | 0 | 0 | 0 | 0 | 0 | 0 | 656744 | 656744 | NFO | Locally | No
Hampton Roads | stip | project | 102980 | Primary | James City County | Facilities For Pedestrians And Bicycles | 3088205 | 0 | 0 | 3088205 | 2026-01-08 | Route 60 (Pocahontas Trail) Widening and Complete Street | 0.352 MI. W. OF INT. HOWARD DRIVE (RTE. 648) | 0.108 MI. E. OF INT. MAGRUDER AVENUE (RTE. 656) | 0060 | Pocahontas Trail | 245.15 | 246.2 | 1.0490 | MI | 5786507 | 12250288 | 30803205 | 48840000 | 48840000 | 2014-06-20 | 2025-10-31 | 2025-10-31 | 2029-02-13 | 2029-02-13 | 2031-07-21 | 48840000 | 0 | 0 | 25427498 | 25427498 | 4658206 | 0 | 0 | 4658206 | NFO | VDOT | No
Hampton Roads | stip | project | 102985 | Urban | Portsmouth | Facilities For Pedestrians And Bicycles | 68218 | 0 | 246133 | 314351 | 2025-03-03 | Westhaven Bicycle Improvements |  |  | U000 | South Street | 1.52 | 2.46 | 1.1500 | MI |  |  |  |  | 314351 | [7 empty] | 0 | 0 | 0 | 0 | 54574.4 | 0 | 245965 | 300539.4 | NFO | Locally | No
Hampton Roads | stip | project | 102990 | Urban | Suffolk | Traffic Management/Engineering | 182164 | 0 | 1045127 | 1227291 | 2025-09-03 | Nansemond Parkway Traffic Signal Upgrades | Intersection of Bridge Road and Shoulders Hill Road | Intersection of Wilroy Road and Route 58 | U000 | Nansemond Parkway | 12.21 | 7.03 |  |  | 182164 |  | 1045127 | 1227291 | 1227291 | 2018-12-20 | 2021-05-06 |  |  | 2021-05-06 | 2024-05-21 | 1696132 | 0 | 0 | 0 | 0 | 145730.85 | 0 | 836101.37 | 981832.22 | NFO | Locally | No
Hampton Roads | stip | project | 102991 | Urban | Suffolk | Traffic Management/Engineering | 181132 | 0 | 1979367 | 2160499 | 2025-11-05 | Bridge Road Traffic Signal Upgrades | College Drive | Eclipse Drive | 0017 | Bridge Road | 33.54 | 40.34 | 6.8000 | MI | 181132 |  | 2138148 | 2319280 | 2319280 | 2018-04-19 | 2020-11-19 |  |  | 2020-11-19 | 2022-10-24 | 2337981 | 0 | 0 | 0 | 0 | 144905.36 | 0 | 1691886 | 1836791.36 | NFO | Locally | Yes
Hampton Roads | stip | project | 102994 | Urban | Suffolk | Traffic Management/Engineering | 195989 | 0 | 1666177 | 1862166 | 2025-10-07 | Suffolk Bypass ITS Improvements | City of Chesapeake limits | Holland Road | 0058 | Suffolk Bypass | 478.52 | 466.71 | 11.6000 | MI | 195989 |  | 1666177 | 1862166 | 1861011 | 2018-01-23 | 2020-12-15 |  |  | 2020-12-15 | 2024-10-08 | 1926728 | 0 | 0 | 0 | 0 | 155866.82 | 0 | 1713980 | 1869846.82 | NFO | Locally | No
Hampton Roads | stip | project | 103005 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 1221525 | 2328928 | 0 | 3550453 | 2026-01-06 | Centerville Turnpike Widening Phase 2 | Kempsville Road | Indian River Road | U000 | Centerville Turnpike | 0 | 1.83 | 1.8300 | MI | 3100963 | 18068637 | 66175888 | 87345488 | 87345488 | 2013-12-26 | 2015-07-29 | 2015-07-29 | 2026-06-30 | 2026-06-30 | 2029-03-28 | 87345488 | 0 | 0 | 0 | 0 | 2544775 | 14618501 | 0 | 17163276 | NFO | Locally | Yes
Hampton Roads | stip | project | 103025 | Urban | Portsmouth | Safety | 551239 | 0 | 0 | 551239 | 2026-01-06 | Portsmouth Traffic Signal Upgrades | Various | Various | U000 | Various | 24.84 | 26.09 | 6.4000 | MI | 720000 |  | 9183006 | 9903006 | 6415053 | 2017-06-29 | 2025-06-26 |  |  | 2025-06-26 | 2026-12-18 | 9903006 | 0 | 0 | 0 | 0 | 576000 | 0 | 3099812 | 3675812 | NFO | Locally | No
Hampton Roads | stip | debt | 103036 | Primary | Hampton Roads District-wide | Bridge, New Construction | 142923520 | 0 | 339661176 | 482584696 | 2025-09-04 | DT/MT/MLK Primary Debt Service | Downtown and Midtown Tunnels; extension of MLK to I-264 | Downtown and Midtown Tunnels; extension of MLK to I-264 | 0058 |  |  |  | 3.9000 | MI | 579256089 |  |  | 579256089 | 564265078 | 2024-08-01: 2012-09-06; 2026-02-28: 2029-06-30 | 564265079 | 44939025 | 0 | 0 | 44939025 | 0 | 0 | 519326052.94 | 519326052.94 | FO | VDOT | Yes
Hampton Roads | stip | debt | 103037 | Interstate | Hampton Roads District-wide | Bridge, New Construction | 4217898 | 0 | 8737376 | 12955274 | 2025-09-04 | DT/MT/MLK Interstate Debt Service | Downtown and Midtown Tunnels; extension of MLK to I-264 | Downtown and Midtown Tunnels; extension of MLK to I-264 | 0264 |  |  |  | 3.9000 | MI | 15283687 |  |  | 15283687 | 14902721 | 2024-08-01: 2012-09-06; 2026-02-28: 2029-06-30 | 14902720 | 943359 | 0 | 60681 | 1004040 | 0 | 0 | 13898681.3 | 13898681.3 | FO | VDOT | Yes
Hampton Roads | stip | project | 103059 | Urban | Newport News | Facilities For Pedestrians And Bicycles | 144403 | 201537 | 581177 | 927116 | 2026-01-06 | Newport News Pedestrian Improvements | Various locations | Various locations | U000 | Citywide | 259.74 | 259.87 |  |  | 144403 | 201537 | 2062692 | 2408632 | 2408632 | 2018-11-16 | 2021-02-26 | 2021-02-26 | 2024-05-30 | 2024-05-30 | 2025-12-04 | 2408632 | 0 | 0 | 0 | 0 | 115522.59 | 161229.25 | 1307248 | 1583999.84 | NFO | Locally | No
Hampton Roads | stip | debt | 103754 | Primary | Statewide |  | 56917372 | 0 | 72047624 | 128964997 | 2025-09-04 | Route 460 PPTA Debt Service | Intersection with Route 58, City of Suffolk | Intersection with I-295, Prince George County | 0460 |  |  |  | 55.0000 | MI | 155924903 |  |  | 155924903 | 152554811 | 2024-08-01: 2012-12-01; 2026-02-28: 2029-06-30 | 152554811 | 15726289 | 0 | 0 | 15726289 | 0 | 0 | 136828521.76 | 136828521.76 | FO | VDOT | Yes
Hampton Roads | stip | budget | 103928 | Miscellaneous | Hampton Roads District-wide | Environmental Only | 5389511 | 0 | 0 | 5389511 | 2025-10-01 | GREEN OPERATOR - NEAR ZERO-EMISSION TRUCKS | N/A | N/A | U000 | N/A |  |  |  |  | 17321002 |  |  | 17321002 | 0 | 2024-08-01: 2014-12-03; 2026-02-28: 2032-02-25 | 17971434 | 5000000 | 0 | 0 | 5000000 | 3856841 | 0 | 0 | 3856841 | NFO | Locally | No
Hampton Roads |  |  | 105623 | Urban | Virginia Beach | Reconstruction w/Added Capacity | 597261 | 29937 | 0 | 627198 |  | Rosemont Road Widening - Phase V | Lynnhaven Parkway | Dam Neck Road |  | Rosemont Road |  |  | 1.5 | MI | 1315000 | 3250000 | 13976000 | 18541000 |  | 2014-07-08 | 2016-06-20 | 2016-06-20 | 2028-08-01 | 2028-08-01 | 2031-11-17 | 18541000 | [8 empty] | NFO | Locality | Yes
Hampton Roads | stip | budget | 106157 | Enhancement | Portsmouth | Facilities For Pedestrians And Bicycles | 221682 | 0 | 675398 | 897080 | 2026-01-06 | Portsmouth Rail to Trail | Portsmouth/Chesapeake city limits | intersection of West Norfolk Road with Old Coast Guard Blvd | EN14 |  | 1.47 | 3.15 | 1.8100 | MI | 268116 |  | 2438424 | 2706540 | 2706540 | 2016-10-28 | 2022-06-22 |  |  | 2022-06-22 | 2024-03-15 | 2986360 | 0 | 0 | 0 | 0 | 214493 | 0 | 685507 | 900000 | NFO | Locally | No
Hampton Roads | stip | project | 106689 | Interstate | Hampton Roads District-wide | Reconstruction W/ Added Capacity | 5766837 | 0 | 102703236 | 108470074 | 2026-01-20 | #HB2.FY17 I-64 CAPACITY IMPROVEMENTS - SEGMENT III | 1.257 Miles West of Rt 199 - Lightfoot (Exit 234) | 1.052 Miles West of Rt 199 - Humelsine Pkwy (Exit 242) | 0064 |  | 233.3 | 241.3 | 8.3560 | MI | 5766837 | 0 | 112893996 | 118660833 | 118660833 | 2016-03-01 | 2017-06-21 | 2017-06-21 | 2017-06-21 | 2017-06-21 | 2021-12-06 | 122893996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FO | VDOT | Yes
Hampton Roads | stip | project | 106692 | Interstate | Chesapeake | Reconstruction W/ Added Capacity | 12189268 | 11780799 | 352041806 | 376011873 | 2026-01-14 | #SMART18 - I-64 Southside Widening and High-Rise Bridge Ph 1 | 0.295 Mile East of I-264 (at Bowers Hill) | 1.018 Mile East of I-464 | 0064 | I-64 | 288.65 | 300.42 | 9.0304 | MI | 12189268 | 18726000 | 401030220 | 431945488 | 431945488 | 2015-02-02 | 2016-12-12 | 2016-12-12 | 2016-12-14 | 2016-12-14 | 2024-10-30 | 431956220 | -10732 | 0 | 1040000 | 1029268 | 0 | 0 | 0 | 0 | FO | VDOT | Yes
Hampton Roads | stip | budget | 106693 | Interstate | Norfolk | Reconstruction W/ Added Capacity | 7510512 | 0 | 0 | 7510512 | 2026-01-06 | I-64/I-264 Interchange-Phase IIIA | 64 | 264 | 0264 | I-264 | 0 | 25.07 | 2.0000 | MI | 7500000 |  |  | 7500000 | 7500000 | 2024-08-01: 2017-02-02; 2026-02-28: 2025-05-27 | 7500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | No
Hampton Roads | stip | project | 107032 | Urban | Chesapeake | Traffic Management/Engineering | 151629 | 0 | 0 | 151629 | 2025-04-16 | Chesapeake Signal Timing - Phase 2 | Various | Various | U000 | Various | 6.08 | 6.08 |  |  | 122650 |  |  | 122650 | 122650 | 2024-08-01: 2020-10-14; 2026-02-28: 2025-01-31 | 173671 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | NFO | Locally | No
Hampton Roads | stip | project | 107033 | Urban | Chesapeake | Traffic Management/Engineering | 114137 | 0 | 0 | 114137 | 2026-01-08 | Chesapeake Signal Timing - Phase 3 | Various | Various | U000 | Various | 6.08 | 6.08 |  |  | 150000 |  |  | 150000 | 150000 | 2024-08-01: 2020-11-17; 2026-02-28: 2025-09-30 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NFO | Locally | No
Hampton Roads | stip | budget | 107035 | Urban | Portsmouth | Safety | 13953 | 0 | 0 | 13953 | 2026-01-06 | George Washington Highway Corridor Improvements | Andrews Street | Mulberry Street | 0141 | George Washington Highway | 0.05 | 0.45 | 0.4000 | MI | 1011340 | 2227060 | 8107948 | 11346348 | 0 | 2022-02-02 | 2026-03-31 | 2026-03-31 | 2029-02-06 | 2029-02-06 | 2030-07-09 | 11346348 | 0 | 0 | 7565628 | 7565628 | 550000 | 0 | 0 | 550000 | NFO | Locally | No
Hampton Roads | stip | budget | 107039 | Urban | Norfolk | Bridge Rehab W/O Added Capacity | 36707 | 0 | 5339451 | 5376158 | 2026-01-15 | Campostella Bridge Rehabilitation | Kimball Terrance | Fillmore Street | 0168 | Campostella Bridge | 22.71 | 22.14 | 0.6000 | MI | 50760 |  | 6332399 | 6383159 | 6383159 | 2021-07-13 | 2023-03-17 |  |  | 2023-03-17 | 2024-09-27 | 6383159 | 0 | 0 | 0 | 0 | 40608 | 0 | 4759392 | 4800000 | NFO | Locally | No
Hampton Roads | stip | budget | 107058 | Urban | Newport News | Safety | 214135 | 0 | 0 | 214135 | 2026-01-06 | #ITTF - Citywide Signal System Upgrade | Washington Ave | Washington Ave | U000 | Washington Ave | 0 | 1.24 |  | MI | 255929 |  | 1654071 | 1910000 | 1910000 | 2022-05-13 | 2025-12-08 |  |  | 2025-12-08 | 2026-10-06 | 1977718 | 0 | 0 | 0 | 0 | 224000 | 0 | 0 | 224000 | NFO | Locally | No
Hampton Roads | stip | project | 107064 | Urban | Virginia Beach | Facilities For Pedestrians And Bicycles | 215296 | 1066 | 0 | 216362 | 2026-01-06 | Bus Stop Infrastructure and Accessibility Improvements | Various | Various | U000 | Various | 20.1 | 20.1 |  |  | 236950 | 151147 | 261200 | 649297 | 649297 | 2021-05-12 | 2024-07-08 | 2024-07-08 | 2026-07-01 | 2026-07-01 | 2027-08-03 | 649297 | 0 | 0 | 0 | 0 | 0 | 120918 | 0 | 120918 | NFO | Locally | No
Hampton Roads | stip | project | 107414 | Secondary | Gloucester County | Facilities For Pedestrians And Bicycles | 398483 | 37317 | 0 | 435801 | 2026-01-20 | ROARING SPRINGS ROAD (SR 616) - RD/PED IMPROVEMENTS | Intersection of Route 17B (Main Street) | 0.39 Miles North of Intersection of Route 17B (Main Street) | 0616 | Roaring Springs Road | 7.46 | 7.85 | 0.3900 | MI | 484576 | 715596 | 1984399 | 3184571 | 3184556 | 2022-06-09 | 2025-09-02 | 2025-09-02 | 2027-05-11 | 2027-05-11 | 2028-03-15 | 3184571 | 0 | 0 | 1587507 | 1587507 | 387661 | 572477 | 0 | 960138 | NFO | VDOT | No
Hampton Roads | stip | budget | 107956 | Enhancement | Virginia Beach | Facilities For Pedestrians And Bicycles | 0 | 102062 | 605494 | 707556 | 2026-01-06 | Thalia Creek Greenway Phase III | Constitution Drive | Independence Blvd | EN12 | various | 0.06 | 0.07 |  | MI |  | 299097 | 2542186 | 2841283 | 2841283 |  |  | 2019-08-16 | 2024-03-07 | 2024-03-07 | 2026-01-14 | 3884749 | 0 | 0 | 0 | 0 | 0 | 239278 | 587209 | 826487 | NFO | Locally | No
Hampton Roads | stip | program | 108041 | Interstate | Virginia Beach | Reconstruction W/ Added Capacity | 238527 | 56129224 | 76650259 | 133018010 | 2026-01-09 | #SMART18 - I-264/WITCHDUCK RD INTERCHANGE & RAMP EXT-C-D RD | 0.466 MILE EAST OF WBL I-64 | 0.472 MILE EAST OF WITCHDUCK RD | 0264 |  |  |  | 2.2200 | MI | 199926 | 56096076 | 79000000 | 135296002 | 135296002 | 2000-12-08 | 2015-04-30 | 2015-04-30 | 2017-07-25 | 2017-07-25 | 2025-10-09 | 127749638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FO | VDOT | Yes
Hampton Roads | stip | program | 108042 | Interstate | Norfolk | Reconstruction W/O Added Capacity | 3500000 | 20458115 | 135151747 | 159109863 | 2025-05-08 | #SMART18 - RTE 264 - INTERCHANGE IMPROVEMENTS-64 WB TO 264EB | 0.757 MILE SOUTH OF CURLEW DRIVE | 0.832 MILE EAST OF WBL I-64 | 0264 |  |  |  | 1.5200 | MI | 3500000 | 20458115 | 137023653 | 160981768 | 160981768 | 2001-02-28 | 2015-04-30 | 2015-04-30 | 2016-04-12 | 2016-04-12 | 2020-05-18 | 152094716 | 0 | 0 | 0 | 0 |  |  |  |  | FO | VDOT | Yes
Hampton Roads | stip | project | 108955 | Urban | Virginia Beach | Traffic Management/Engineering | 366338 | 0 | 0 | 366338 | 2025-06-20 | Corridor Retiming - Kempsville Rd & Newtown Area | Kempsville Road | Newtown Road | U000 | Various | 51.079 | 53 |  |  | 366338 |  |  | 366338 | 366338 | 2024-08-01: 2023-03-02; 2026-02-28: 2025-06-10 | 521180 | 0 | 0 | 0 | 0 | 0 | 0 | 416944 | 416944 | NFO | Locally | No
Hampton Roads | stip | project | 108959 | Urban | Virginia Beach | Traffic Management/Engineering | 143036 | 0 | 0 | 143036 | 2026-01-06 | Traffic Adaptive Corridor Implementation | Leland Circle | Pleasant Valley Road | U000 | Indian River Road | 12.4 | 15.28 | 4.3000 | MI | 390000 |  | 649676 | 1039676 | 1039676 | 2023-03-01 | 2026-09-30 |  |  | 2026-09-30 | 2027-09-30 | 980614 | 0 | 0 | 0 | 0 | 312000 | 0 | 0 | 312000 | NFO | Locally | No
Hampton Roads | stip | project | 108966 | Urban | Virginia Beach | Traffic Management/Engineering | 207835 | 98 | 0 | 207934 | 2026-01-06 | Rosemont Rd/South Plaza Trail Intersection Improvements | Rosemont Road | S. Plaza Trail | 0411 | South Plaza Trail | 0 | 4.12 | 0.6100 | MI | 255366 | 121911 | 1473866 | 1851143 | 1851143 | 2023-01-20 | 2025-07-31 | 2025-07-31 | 2027-04-30 | 2027-04-30 | 2028-05-02 | 1851143 | 0 | 0 | 1347161 | 1347161 | 152649 | 97529 | 0 | 250178 | NFO | Locally | No
Hampton Roads | stip | project | 108980 | Urban | Newport News | Facilities For Pedestrians And Bicycles | 206476 | 27910 | 0 | 234386 | 2026-01-06 | Briarfield Sidewalk | Marshall Avenue | Chestnut Avenue | U000 | Briarfield Road | 10.12 | 10.18 | 0.5100 | MI | 217136 | 108000 | 1570000 | 1895136 | 1588402 | 2020-04-02 | 2024-04-04 | 2024-04-04 | 2026-05-11 | 2026-05-11 | 2027-11-22 | 1588402 | 0 | 0 | 0 | 0 | 177600 | 86400 | 0 | 264000 |  | Locally | No
Hampton Roads | stip | project | 108981 | Urban | Newport News | Facilities For Pedestrians And Bicycles | 247544 | 6572 | 0 | 254116 | 2026-01-06 | Warwick Boulevard Sidewalk Widening | Lucas Creek Road | Atkinson Way | U000 | Warwick Boulevard | 253.44 | 255.13 | 1.5000 | MI | 250000 | 216000 | 1182082 | 1648082 | 1648082 | 2020-04-02 | 2024-08-07 | 2024-08-07 | 2027-01-18 | 2027-01-18 | 2028-09-12 | 1648083 | 0 | 0 | 945665 | 945665 | 150372 | 172800 | 0 | 323172 |  | Locally | No
Hampton Roads | stip | project | 108982 | Urban | Suffolk | Other | 95855 | 0 | 31739 | 127594 | 2026-01-06 | Suffolk Transportation Operation Center | 800 Carolina Road, Suffolk, VA 23434 | 800 Carolina Road, Suffolk, VA 23434 | U000 |  | 10.77 | 10.97 |  |  | 120000 |  | 3002830 | 3122830 | 3122830 | 2022-01-10 | 2024-04-11 |  |  | 2024-04-11 | 2026-03-31 | 3122839 | 0 | 0 | 0 | 0 | 96000 | 0 | 0 | 96000 |  | Locally | No
Hampton Roads | stip | project | 108983 | Urban | Suffolk | Traffic Management/Engineering | 113220 | 0 | 0 | 113220 | 2026-01-08 | SUFFOLK CITYWIDE SIGNAL TIMINGS AND EQUIPMENT INSTALLATION | Citywide | Various Locations | U000 |  | 0.59 | 0.59 |  |  | 300000 |  | 426681 | 726681 | 726681 | 2022-04-18 | 2025-11-20 |  |  | 2025-11-20 | 2026-11-12 | 726681 | 0 | 0 | 0 | 0 | 240000 | 0 | 0 | 240000 |  | Locally | No
Hampton Roads | stip | project | 108984 | Urban | Suffolk | Bridge Replacement W/O Added Capacity | 27992 | 177 | 0 | 28169 | 2026-01-06 | #SGR18LB - Speights Spillway Bridge Replacement | Turlington Road | Turlington Road | U000 | Turlington Road | 1.06 | 1.08 | 0.1000 | MI | 275000 | 20000 | 1698145 | 1993145 | 1374500 | 2019-05-22 | 2025-03-26 | 2025-03-26 | 2025-12-02 | 2025-12-02 | 2026-12-25 | 1993145 | 0 | 0 | 24500 | 24500 | 220000 | 16000 | 0 | 236000 |  | Locally | No
Hampton Roads | stip | program | 108990 | Interstate | Chesapeake | Reconstruction W/ Added Capacity | 0 | 0 | 92657685 | 92657685 | 2023-04-04 | #SMART18 - I-64 Southside Widening & High-Rise Bridge Ph 1 | I-464 | I-664/I-264 | 0064 | I-64 |  |  | 8.2100 | MI |  |  | 92657545 | 92657545 | 92657545 | 2026-10-01: 2016-12-14; 2029-03-31: 2024-10-31 | 92657545 | 0 | 0 | 18931958 | 18931958 | 0 | 0 | 0 | 0 | FO | VDOT | Yes
Hampton Roads | stip | project | 109075 | Public Transportation | Newport News | Transit | 0 | 0 | 9263145 | 9263145 | 2024-02-29 | Amtrak Multimodal Station - Site Grading and Drainage | SW of Intersection of CSX RR and | Bland Boulevard | U000 |  | 254.62 | 254.83 |  |  |  |  | 9728350 | 9728350 | 9728350 | 2026-10-01: 2020-02-25; 2029-03-31: 2024-05-31 | 9728350 | 0 | 0 | 0 | 0 | 0 | 0 | 5962138 | 5962138 | NFO | Locally | No
Hampton Roads | stip | project | 109076 | Public Transportation | Newport News | Transit | 0 | 0 | 15271990 | 15271990 | 2025-09-03 | Amtrak Multimodal Station - Station, Platform, Parking Lot | SW of Intersection of CSX RR and | Bland Boulevard | U000 |  | 254.6 | 254.92 |  |  |  |  | 18685716 | 18685716 | 18685716 | 2026-10-01: 2020-04-14; 2029-03-31: 2024-02-29 | 18685716 | 0 | 0 | 0 | 0 | 0 | 0 | 12751150 | 12751150 | NFO | Locally | No
Hampton Roads | stip | project | 109314 | Secondary | Isle of Wight County | New Construction Roadway | 1814272 | 3369601 | 9641856 | 14825729 | 2026-01-13 | #HB2.FY17 NIKE PARK RD EXTENSION FROM REYNOLDS DR TO RTE 17 | 0.052 MLES NORTH OF ROUTE 665 | 0.0018 MLES WEST OF ROUTE 17 | 0669 | Nike Park | 1.44 | 1.44 | 0.9320 | MI | 1814272 | 3719181 | 11429932 | 16963385 | 16963385 | 2016-10-24 | 2022-06-09 | 2022-06-09 | 2024-03-12 | 2024-03-12 | 2026-07-10 | 17007666 | 0 | 0 | 1234198 | 1234198 | 1804602.37 | 2848301 | 10195734 | 14848637.37 |  | VDOT | No
Hampton Roads | stip | project | 109381 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 535382 | 0 | 0 | 535382 | 2025-06-03 | #HB2.FY17 Centerville Turnpike - Phase III | .43 Mile South of Lynnhaven Parkway | .75 Mile North of Lynnhaven Parkway | U000 | Centerville Turnpike | 1.82 | 2.94 | 1.1500 | MI | 3134597 | 11344638 | 83001605 | 97480840 | 97480840 | 2016-10-26 | 2025-07-11 | 2025-07-11 | 2027-06-16 | 2027-06-16 | 2029-04-24 | 61571698 | 0 | 0 | 0 | 0 | 2292299.4 | 0 | 0 | 2292299.4 | NFO | Locally | Yes
Hampton Roads |  |  | 109382 | Primary | Chesapeake | Bridge Rehab w/ Added Capacity | [5 empty] | Deek Creek Bridge Replacement | George Washington Highway North | Slightly west of Cedar Pointe Lane |  | Moses Grandy Trail |  |  | 0.79 | MI | 70510 | 9840000 | 69487000 | 79397510 |  | 2015-05-28 | 2019-11-21 | 2019-11-21 | 2022-07-14 | 2022-07-14 | 2027-09-13 | 85871000 | [9 empty] | Army Corp of Engineers | Yes
Hampton Roads | stip | debt | 109383 | Interstate | Hampton Roads District-wide | Other | 6011115 | 0 | 65929322 | 71940437 | 2025-09-04 | I-64 CAPACITY IMPROVEMENTS - SEGMENT I - DEBT SERVICE | 0.50 miles east of Route 238 (Yorktown Road) | 1.55 miles west of Route 143 (Jefferson Ave) | 0064 |  |  |  | 5.6700 | MI | 100692685 |  |  | 100692685 | 98237318 | 2024-08-01: 2016-06-16; 2026-02-28: 2032-06-30 | 97478185 | 17531129 | 0 | 0 | 17531129 | 0 | 0 | 68965740.78 | 68965740.78 | FO | VDOT | Yes
Hampton Roads | stip | project | 109410 | Urban | Hampton | Traffic Management/Engineering | 1258160 | 0 | 0 | 1258160 | 2026-01-06 | Traffic Signal System Retimings Phase II | Various | Various | U000 | Various | 0 | 0.15 |  |  | 2129447 |  |  | 2129447 | 2129447 | 2024-08-01: 2021-08-04; 2026-02-28: 2027-01-01 | 2129447 | 0 | 0 | 0 | 0 | 0 | 0 | 844000 | 844000 |  | Locally | No
Hampton Roads | stip | project | 109418 | Urban | Chesapeake | Traffic Management/Engineering | 41924 | 0 | 0 | 41924 | 2025-07-30 | Chesapeake Signal Timing & Incident Management Plans | Various | Various | U000 | Various | 6.08 | 6.08 |  |  | 150000 |  |  | 150000 | 150000 | 2024-08-01: 2022-01-28; 2026-02-28: 2025-12-16 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | NFO | Locally | No
Hampton Roads |  |  | 109572 | Public Transportation | Hampton Roads Transit | Transit | [5 empty] | HRT Bus Shelters and Pedestrian Improvements in Norfolk | [8 empty] | 75000 | 0 | 1216509 | 1291509 |  | 2021-04-21 | 2026-12-31 |  |  | 2027-01-01 | 2028-03-31 | 1291509 | [8 empty] | FO | HRT-DRPT | No
Hampton Roads | stip | program | 109790 | Interstate | York County | Reconstruction W/ Added Capacity | 0 | 975941 | 98359577 | 99335518 | 2026-01-20 | #HB2.FY17 I-64 CAPACITY IMPROVEMENTS - SEGMENT III | 1.15 Mile West of Rt 199 - Lightfoot (Exit 234) | 1.05 Miles West of Rt 199 - Humelsine Pkwy (Exit 242) | 0064 |  |  |  | 8.2500 | MI |  | 12000000 | 109151977 | 121151977 | 121151977 |  |  | 2017-06-21 | 2017-06-21 | 2017-06-21 | 2021-12-06 | 121151977 | 0 | 0 | 0 | 0 | 0 | 33323203.37 | 84699456.63 | 118022660 | FO | VDOT | Yes
Hampton Roads | stip | debt | 110385 | Urban | Norfolk |  | 0 | 0 | 33318173 | 33318173 | 2025-09-04 | RTE 165 - 6 & 8 LANES DEBT SERVICE GARVEE DEBT SERVICE |  |  | 0165 | [5 empty] | 60264462 |  |  | 60264462 | 1394043 | 2024-08-01: 2017-03-01; 2026-02-28: 2034-06-30 | 54979684 | 137162 | 0 | 0 | 137162 | 368140.72 | 0 | 21691921.89 | 22060062.61 |  | VDOT | TBD
Hampton Roads | stip | debt | 110386 | Urban | Virginia Beach |  | 0 | 0 | 10595430 | 10595430 | 2025-09-04 | #HB2.FY17 INDIAN RIVER RD Ph 7A GARVEE DEBT SERVICE |  |  | U000 | [5 empty] | 24608002 |  |  | 24608002 | 8600516 | 2024-08-01: 2017-03-01; 2026-02-28: 2039-06-30 | 19436299 | 1867673 | 0 | 0 | 1867673 | 0 | 6322522.29 | 4293060.91 | 10615583.2 |  | VDOT | TBD
Hampton Roads | stip | debt | 110387 | Urban | Norfolk |  | 0 | 0 | 2912079 | 2912079 | 2025-09-04 | ROBIN HOOD RD & MILITARY HWY PHASE 1 GARVEE DEBT SERVICE |  |  | 0165 | [5 empty] | 5067313 |  |  | 5067313 | 1394043 | 2024-08-01: 2017-03-01; 2026-02-28: 2032-06-30 | 4185717 | 137162 | 0 | 0 | 137162 | 0 | 0 | 2348216.53 | 2348216.53 |  | VDOT | TBD
Hampton Roads | stip | debt | 110389 | Urban | Suffolk |  | 0 | 0 | 4497040 | 4497040 | 2025-09-04 | #HB2.FY17 RTE 58/ HOLLAND RD. Corridor GARVEE DEBT SERVICE |  |  | 0058 | [5 empty] | 53362764 |  |  | 53362764 | 14406108 | 2024-08-01: 2017-03-01; 2026-02-28: 2039-06-30 | 23744574 | 6733520 | 0 | 0 | 6733520 | 0 | 299476.92 | 7476235.35 | 7775712.27 |  | VDOT | TBD
Hampton Roads | stip | project | 110626 | Urban | Gloucester County | Facilities For Pedestrians And Bicycles | 642867 | 138134 | 0 | 781001 | 2026-01-20 | RTE 1208 - PEDESTRIAN IMPROVEMENT (GREATE ROAD) | 0.522 MI S of Lafayette Heights Drive | 0.006 MI N of Lafayette Heights Drive | 1208 | Greate Road | 0 | 0.74 | 0.5280 | MI | 782361 | 723369 | 3165935 | 4671665 | 4435571 | 2019-11-04 | 2025-06-10 | 2025-06-10 | 2027-01-06 | 2027-01-06 | 2028-05-04 | 4671665 | 0 | 0 | 1629111 | 1629111 | 528000 | 578696 | 0 | 1106696 | NFO | VDOT | No
Hampton Roads | stip | project | 110627 | Primary | Gloucester County | Safety | 1136341 | 0 | 0 | 1136341 | 2026-01-06 | RTE 17 - WIDENING PHASE 1 - GEORGE WASHINGTON MEMORIAL HIGHW | 0.015 MI SOUTH OF ROUTE 1237 (FARMWOOD ROAD) | 0.306 MI NORTH OF ROUTE 641 (TIDEMILL ROAD) | 0017 | GEORGE WASHINGTON MEMORIAL HIGHWAY | 69.63 | 71.08 | 0.9970 | MI | 2350729 | 7019874 | 33047905 | 42418508 | 42418508 | 2023-05-31 | 2026-12-15 | 2026-12-15 | 2028-12-12 | 2028-12-12 | 2030-09-17 | 42418508 | 0 | 5392427 | 26661796 | 32054223 | 3742851 | 0 | 0 | 3742851 | FO | VDOT | Yes
Hampton Roads | stip | project | 110634 | Urban | Suffolk | New Construction Roadway | 1614122 | 2937957 | 14237401 | 18789479 | 2026-01-09 | Nansemond Pkwy/Wilroy Rd Overpass over Commonwealth Railway | South of Nansemond Rkwy/Wilroy Intersection | North of Bridlewood Lane/Nansemond Parkway | U000 |  | 6.84 | 7.31 | 0.7200 | MI | 1614122 | 4456793 | 21670855 | 27741770 | 27741770 | 2017-08-09 | 2021-04-09 | 2021-04-09 | 2023-03-31 | 2023-03-31 | 2025-10-30 | 27727648 | 0 | 0 | 0 | 0 | 1614121.64 | 4336135 | 0 | 5950256.64 |  | Locally | No
Hampton Roads | stip | project | 110757 | Urban | Portsmouth | Traffic Management/Engineering | 1296 | 0 | 0 | 1296 | 2026-01-06 | Portsmouth Citywide Signal Timing - Phase 1 (PE Only) | Various | Various | U000 | Citywide | 26.1 | 26.1 |  |  | 120000 |  |  | 120000 | 120000 | 2024-08-01: 2025-02-25; 2026-02-28: 2027-06-17 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 96000 | 96000 |  | Locally | No
Hampton Roads | stip | project | 110801 | Urban | Chesapeake | Traffic Management/Engineering | 1349 | 0 | 0 | 1349 | 2026-01-06 | Citywide Signal System Upgrade with Feasibility Study | Various | Various | U000 | Various | 6.08 | 6.08 | 0.0000 | MI | 200000 |  | 3912000 | 4112000 | 4112000 | 2025-08-20 | 2027-03-16 |  |  | 2027-03-16 | 2028-03-01 | 4112000 | 0 | 0 | 3341902 | 3341902 | 160000 | 0 | 0 | 160000 | NFO | Locally | No
Hampton Roads | stip | project | 110802 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 129269 | 0 | 0 | 129269 | 2026-01-06 | Dam Neck Road/Holland Road Intersection Improvements | Dam Neck | Holland Road | U000 | Dam Neck Road | 6.7 | 6.74 | 0.0000 | MI | 270900 | 64071 | 2995838 | 3330809 | 3330809 | 2023-01-10 | 2026-03-05 | 2026-03-05 | 2028-06-28 | 2028-06-28 | 2029-12-14 | 3330809 | 0 | 0 | 2254647 | 2254647 | 272000 | 0 | 0 | 272000 | NFO | Locally | No
Hampton Roads | stip | project | 110803 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 1193286 | 0 | 0 | 1193286 | 2026-01-06 | #SMART18 - Cleveland Street Phase IV | Witchduck Road | Independence Boulevard | U000 | Cleveland Street | 0 | 0.79 | 1.2000 | MI | 2851407 | 17071668 | 37414576 | 57337651 | 57337651 | 2019-11-07 | 2026-09-01 | 2026-09-01 | 2029-11-01 | 2029-11-01 | 2032-12-08 | 25347000 | 0 | 0 | 0 | 0 | 2745508 | 0 | 0 | 2745508 |  | Locally | Yes
Hampton Roads | stip | project | 110804 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 24492 | 0 | 0 | 24492 | 2026-01-16 | #SMART18 - Indian River Road Phase 7B | Lynnhaven Parkway | Elbow Road | U000 | Indian River Road | 9.36 | 11.5 | 2.2000 | MI | 2175000 | 2181400 | 19268709 | 23625109 | 23625109 | 2020-02-24 | 2027-03-01 | 2027-03-01 | 2031-07-02 | 2031-07-02 | 2034-05-03 | 20879070 | 0 | 2181400 | 0 | 2181400 | 1370351 | 0 | 0 | 1370351 | NFO | Locally | Yes
Hampton Roads | stip | project | 111018 | Urban | Williamsburg | Reconstruction W/ Added Capacity | 56194 | 0 | 0 | 56194 | 2026-01-06 | #SMART18 - IRONBOUND ROAD IMPROVEMENTS - PHASE 2 | Treyburn Rd. | Richmond Rd. | 7081 | Ironbound Rd | 0 | 1.16 | 0.5000 | MI | 310100 | 469000 | 1143600 | 1922700 | 1922700 | 2021-10-26 | 2027-03-30 | 2027-03-30 | 2029-06-27 | 2029-06-27 | 2030-12-25 | 1922700 | 0 | 469000 | 1143600 | 1612600 | 0 | 0 | 0 | 0 | NFO | Locally | Yes
Hampton Roads | stip | project | 111020 | Urban | Williamsburg | Reconstruction W/ Added Capacity | 79692 | 0 | 0 | 79692 | 2026-01-06 | #SMART18 - IRONBOUND ROAD IMPROVEMENTS - PHASE 3 | Treyburn Drive | DePue Drive | 7081 | Ironbound Rd | 0 | 1.16 | 1.0000 | MI | 451600 | 1117100 | 1743700 | 3312400 | 3312400 | 2021-10-20 | 2027-03-30 | 2027-03-30 | 2029-06-27 | 2029-06-27 | 2030-12-25 | 3312400 | 0 | 2228200 | 1743700 | 3971900 | 0 | 0 | 0 | 0 | NFO | Locally | Yes
Hampton Roads | stip | project | 111036 | Urban | Suffolk | Traffic Management/Engineering | 1466930 | 0 | 0 | 1466930 | 2026-01-06 | Route 58 IMR (Study Only) | Wilroy Road Interchange | Pitchkettle Road Interchange | 0058 | Route 58 | 468.32 | 472.71 | 4.8000 | MI | 2071186 |  |  | 2071186 | 2001186 | 2024-08-01: 2023-01-06; 2026-02-28: 2027-07-14 | 2071186 | 949 | 0 | 0 | 949 | 0 | 0 | 2000000 | 2000000 |  | Locally | No
Hampton Roads | stip | project | 111081 | Urban | Newport News | Safety | 7021 | 0 | 0 | 7021 | 2026-01-06 | Citywide Newport News Citywide Signal System Progression | Washington Ave | Washington Ave | U000 | Washington AVE | 0 | 1.24 | 0.0000 | MI | 400000 |  | 1850000 | 2250000 | 2250000 | 2024-04-18 | 2027-06-30 |  |  | 2027-06-30 | 2028-06-15 | 1250000 | 0 | 0 | 0 | 0 | 168000 | 0 | 0 | 168000 | NFO | Locally | No
Hampton Roads | stip | project | 111083 | Urban | Suffolk | Rail/Highway Crossing | 4804 | 0 | 0 | 4804 | 2026-01-08 | City of Suffolk Dowtown Railroad Warning System | North Main Street | North Main Street | U000 | North Main Street | 0.59 | 0.59 |  |  | 150000 |  | 500000 | 650000 | 650000 | 2024-01-26 | 2026-04-03 |  |  | 2026-04-03 | 2027-07-16 | 650000 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 120000 | NFO | Locally | No
Hampton Roads | stip | project | 111086 | Urban | Suffolk | Safety | 107834 | 0 | 0 | 107834 | 2026-01-06 | City of Suffolk Citywide Signal System Upgrade | Various Locations | Various Locations | U000 | Citywide | 0.59 | 0.59 |  |  | 159000 |  | 1435000 | 1594000 | 1594000 | 2024-01-18 | 2026-03-27 |  |  | 2026-03-27 | 2027-07-14 | 1594000 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 120000 | NFO | Locally | No
Hampton Roads | stip | project | 111088 | Urban | Suffolk | Safety | 125982 | 0 | 0 | 125982 | 2026-01-06 | City of Suffolk Dowtown Signal System Upgrade | Various Locations | Citywide | U000 |  | 0.59 | 0.59 |  |  | 200000 |  | 1450000 | 1650000 | 1650000 | 2024-01-04 | 2026-04-17 |  |  | 2026-04-17 | 2027-07-16 | 1650000 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 120000 | NFO | Locally | No
Hampton Roads | stip | project | 111089 | Urban | Suffolk | Reconstruction W/O Added Capacity | 375371 | 828304 | 765795 | 1969469 | 2026-01-15 | Crittenden Road and Route 17 Intersection Realignment | Crittenden Road | Clubhouse Road and Bridge Road | U000 | Crittenden Road | 5.26 | 5.31 | 0.1100 | MI | 797000 | 3440661 | 8235447 | 12473108 | 12473108 | 2019-01-22 | 2021-01-13 | 2021-01-13 | 2025-01-24 | 2025-01-24 | 2026-12-14 | 12473108 | 0 | 0 | 0 | 0 | 637600.09 | 2491163.91 | 0 | 3128764 | NFO | Locally | No
Hampton Roads | stip | program | 111237 | Primary | James City County | Safety | [5 empty] | JAMES CITY COUNTY TRANSPORTATION MASTER PLAN | VARIOUS | VARIOUS | 9999 | Various Locations Throught the County |  |  |  |  | 50000 |  |  | 50000 | 50000 | 2024-08-01: 2023-01-05; 2026-02-28: 2024-07-25 | 50000 | 0 | 0 | 0 | 0 |  |  |  |  | FO | Locally | No
Hampton Roads | stip | project | 111308 | Enhancement | Virginia Beach | Facilities For Pedestrians And Bicycles | 186194 | 0 | 594948 | 781142 | 2025-09-03 | Foxfire Pedestrian Trail - Ph 1 | North Landing Road | Foxfire Park/Esplanade Drive | EN17 | Foxfire Trail | 19.87 | 19.87 | 1.0000 | MI | 230000 |  | 739044 | 969044 | 969044 | 2018-01-24 | 2023-02-13 |  |  | 2023-02-13 | 2024-12-31 | 2537798 | 0 | 0 | 0 | 0 | 184000 | 0 | 591235 | 775235 | NFO | Locally | No
Hampton Roads | stip | project | 111427 | Interstate | Chesapeake | Reconstruction W/ Added Capacity | 9658216 | 0 | 0 | 9658216 | 2026-01-14 | Bowers Hill Interchange | I64I264 | I664 | 0664 | I-664 | 12.02 | 20.79 |  |  | 11904630 |  |  | 11904630 | 11904630 | 2024-08-01: 2017-10-02; 2026-02-28: 2024-09-18 | 11904630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | No
Hampton Roads | stip | project | 111711 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | 1102283 | 4086527 | 61432033 | 66620844 | 2026-01-09 | #SMART18 - Laskin Road Phase 1-A | Republic Road | Fremac Drive | 0058 | Laskin Road | 506.5 | 507.56 | 1.0000 | MI | 1102283 | 4742861 | 63860252 | 69705396 | 69705396 | 2017-12-06 | 2018-10-10 | 2018-10-10 | 2019-01-22 | 2019-01-22 | 2026-07-30 | 72470574 | 0 | 0 | 0 | 0 | 1099726.23 | 0 | 40979573 | 42079299.23 | NFO | VDOT | Yes
Hampton Roads | stip | project | 111787 | Primary | York County | Reconstruction W/ Added Capacity | 2165463 | 3191508 | 0 | 5356971 | 2026-01-09 | #SMART18 - Route 17 Widening between Rte 630 and Rte 173 | 0.149 mi. S. Int. Grafton Dr. | 0.266 mi. S. Int. Old York-Hampton Hwy (Route 634) | 0017 | George Washington Memorial Highway | 62.46 | 63.17 | 0.7120 | MI | 2427598 | 9183613 | 16292929 | 27904140 | 27904140 | 2018-09-10 | 2023-10-12 | 2023-10-12 | 2026-11-10 | 2026-11-10 | 2029-10-10 | 27904140 | 0 | 0 | 15024072 | 15024072 | 2427598 | 8287900 | 0 | 10715498 | NFO | VDOT | Yes
Hampton Roads | stip | project | 111791 | Primary | York County | Reconstruction W/ Added Capacity | 836234 | 469043 | 2093587 | 3398864 | 2026-01-13 | #SMART18 - Route 171 Widening between Route 17 and Route 134 | 0.009 Miles East of Route 17 (George Washington Hwy) | 0.016 Miles West of Route 134 (Hampton Hwy) | 0171 | Victory Boulevard | 2.43 | 2.8 | 0.3450 | MI | 840000 | 468765 | 3741568 | 5050333 | 5050333 | 2019-12-26 | 2022-11-16 | 2022-11-16 | 2024-10-08 | 2024-10-08 | 2026-02-03 | 5188804 | 0 | 0 | 0 | 0 | 0 | 675411 | 2343461 | 3018872 | NFO | VDOT | Yes
Hampton Roads | stip | debt | 111982 | Interstate | Chesapeake |  | 0 | 0 | 56267823 | 56267823 | 2025-09-04 | #SMART18 I-64 SS Widen & High-Rise Br Ph 1 DEBT SERVICE |  |  | 0064 | [5 empty] | 113996386 |  |  | 113996386 | 33525841 | 2024-08-01: 2018-03-15; 2026-02-28: 2034-06-30 | 98701931 | 6214955 | 0 | 0 | 6214955 | 0 | 0 | 63983656 | 63983656 |  | VDOT | TBD
Hampton Roads | stip | project | 112317 | Urban | Virginia Beach | New Construction Roadway | 345060 | 0 | 6712435 | 7057495 | 2026-01-06 | Elbow Road Phase 2C | Indian River Road | Salem Road | U000 | Elbow Road | 0 | 1.11 | 1.1000 |  | 900000 |  | 37380000 | 38280000 | 38280000 | 2019-01-10 | 2023-08-23 |  |  | 2023-08-23 | 2026-09-18 | 38280000 | 0 | 0 | 0 | 0 | 800000 | 0 | 21547309 | 22347309 | NFO | Locally | Yes
Hampton Roads | stip | project | 112318 | Urban | Virginia Beach | New Construction Roadway | 393595 | 0 | 0 | 393595 | 2026-01-06 | Elbow Road Phase 2D | Salem Road | Ampitheathre West Parking Area | U000 | Elbow Road/Dam Neck | 22.561 | 23.684 | 1.2000 | MI | 2896800 | 4451900 | 46372228 | 53720928 | 53720928 | 2023-06-21 | 2027-06-15 | 2027-06-15 | 2028-11-27 | 2028-11-27 | 2031-04-29 | 33430613 | 0 | 0 | 0 | 0 | 1960530 | 0 | 0 | 1960530 | NFO | Locally | Yes
Hampton Roads | stip | project | 113830 | Urban | Portsmouth | Safety | 23924 | 0 | 80 | 24003 | 2026-01-06 | Install Emergency Vehicle Preemption Software & Hardware | Various | Various | U000 | Citywide | 25.02 | 25.02 |  |  | 24049 |  | 699932 | 723981 | 723981 | 2019-05-08 | 2025-03-21 |  |  | 2025-03-21 | 2026-06-16 | 723981 | 0 | 0 | 0 | 0 | 19239 | 0 | 0 | 19239 | NFO | Locally | No
Hampton Roads | stip | project | 113866 | Urban | Norfolk | Traffic Management/Engineering | 57173 | 0 | 246827 | 304000 | 2025-08-12 | Emergency Vehicle Preemption - Norfolk | Various | Various | U000 | Various | 27.29 | 27.3 | 0.0000 | MI | 57173 |  | 247072 | 304245 | 304245 | 2019-01-30 | 2022-08-26 |  |  | 2022-08-26 | 2023-11-21 | 363783 | 0 | 0 | 0 | 0 | 45738.36 | 0 | 217461.64 | 263200 | NFO | Locally | Yes
Hampton Roads | stip | project | 115008 | Interstate | Multi-jurisdictional: Hampton Roads MPO | Bridge, New Construction | 0 | 0 | 2349118362 | 2349118362 | 2025-12-23 | I-64 HRBT Expansion Project - Design-Build Contract | Settlers Landing Road | I-564 | 0064 | I64 | 267.39 | 277.31 |  |  | 0 |  | 3004569251 | 3004569251 | 3004569251 | 2017-01-03 | 2018-10-18 |  |  | 2018-10-18 | 2027-08-27 | 3004569251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FO | VDOT | Yes
Hampton Roads | stip | program | 115009 | Interstate | Multi-jurisdictional: Hampton Roads MPO | Other | 139721417 | 9561693 | 200580601 | 349863711 | 2026-01-16 | I-64 HRBT Expansion Project - Owners Oversight | Settlers Landing Road | I-564 | 0064 | I64 |  |  |  |  | 118472054 | 15000000 | 415428276 | 548900330 | 548900330 | 2019-04-30 | 2027-08-27 | 2019-04-30 | 2021-04-01 | 2019-04-30 | 2027-08-27 | 615112469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FO | VDOT | Yes
Hampton Roads | stip | program | 115010 | Interstate | Multi-jurisdictional: Hampton Roads MPO | Other | 0 | 0 | 200000000 | 200000000 | 2023-09-22 | #SMART20 I-64 HRBT Expansion Project - Design-Build Contract | Settlers Landing Road | I-564 | 0064 | I64 | [6 empty] | 200000000 | 200000000 | 200000000 | 2026-10-01: 2019-04-30; 2029-03-31: 2027-08-27 | 200000000 | 0 | 0 | 0 | 0 | 0 | 0 | 195047574.1 | 195047574.1 | FO | VDOT | Yes
Hampton Roads | stip | program | 115011 | Interstate | Multi-jurisdictional: Hampton Roads MPO | Bridge Replacement W/ Added Capacity | 8658764 | 0 | 93076831 | 101735594 | 2026-01-20 | #SGR20VB - I-64 HRBT Expansion Project - South Trestles | Willoughby Spit Shoreline | HRBT South Island Shoreline | 0064 | I64 |  |  |  |  | 3527946 |  | 104999700 | 108527646 | 108527646 | 2019-04-30 | 2027-08-27 |  |  | 2019-04-30 | 2027-08-27 | 108527646 | 0 | 0 | 0 | 0 | 3527946 | 0 | 85783828.65 | 89311774.65 | FO | VDOT | Yes
Hampton Roads | stip | project | 115244 | Urban | Norfolk | Reconstruction W/ Added Capacity | [5 empty] | #SMART20 Virginia Beach Blvd Widening – George St to Newtown | Newtown Road | George Street | 0058 | Virginia Beach Blvd | 498.2 | 498.64 | 0.4440 | MI | 1242538 | 5749694 | 8708789 | 15701021 | 15701021 | 2025-12-01 | 2028-04-17 | 2028-04-17 | 2028-04-18 | 2028-04-18 | 2031-02-12 | 15701021 | 0 | 1751852 | 8708789 | 10460641 | 0 | 0 | 0 | 0 |  | Locally | Yes
Hampton Roads | stip | project | 115370 | Urban | Norfolk | Traffic Management/Engineering | 1621 | 0 | 0 | 1621 | 2026-01-06 | Traffic Signal Detection Upgrades | Various | Various | U000 | Various | 26.88 | 26.88 |  |  | 106946 |  | 893054 | 1000000 | 1000000 | 2025-06-23 | 2026-06-30 |  |  | 2026-06-30 | 2027-11-17 | 1000000 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 80000 |  | Locally | No
Hampton Roads | stip | project | 115371 | Urban | Virginia Beach | Traffic Management/Engineering | 101323 | 0 | 0 | 101323 | 2026-01-06 | N. Great Neck/London Bridge & Virginia Beach Blvd Int Improv | London Bridge Rd | Virginia Beach Blvd | 0058 | N. Great Neck Rd. | 0 | 0.03 |  |  | 495274 |  | 2272721 | 2767995 | 2767995 | 2024-07-14 | 2027-12-27 |  |  | 2027-12-27 | 2028-12-13 | 2767995 | 0 | 0 | 1818177 | 1818177 | 396219 | 0 | 0 | 396219 |  | Locally | No
Hampton Roads | stip | project | 115372 | Urban | Norfolk | Traffic Management/Engineering | 24700 | 0 | 0 | 24700 | 2026-01-06 | Transportation Information and Decision Support System | Various | Various | U000 | Various | 0 | 0.19 |  |  | 100000 |  | 700000 | 800000 | 800000 | 2025-06-05 | 2026-09-17 |  |  | 2026-09-17 | 2028-01-07 | 800000 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 80000 |  | Locally | No
Hampton Roads | stip | project | 115373 | Urban | Newport News | Traffic Management/Engineering | [5 empty] | Opticom Emergency Vehicle Preemption (EVP) | Various - Newport news wide | Various - Newport News wide | U000 |  | 267.44 | 267.44 |  |  | 50000 |  | 725000 | 775000 | 775000 | 2025-12-04 | 2028-07-07 |  |  | 2028-07-07 | 2029-10-30 | 775000 | 0 | 0 | 635000 | 635000 | 0 | 0 | 0 | 0 |  | Locally | No
Hampton Roads | stip | project | 115376 | Urban | Newport News | Traffic Management/Engineering | [5 empty] | Permanent Message Boards | Various - Newport News Wide | Various - Newport News Wide | U000 |  | 267.44 | 267.44 |  |  | 175000 | 50000 | 1020412 | 1245412 | 1230000 | 2025-11-25 | 2028-06-30 | 2028-06-30 | 2030-04-05 | 2030-04-05 | 2031-03-24 | 1245412 | 0 | 40000 | 808000 | 848000 | 0 | 0 | 0 | 0 |  | Locally | No
Hampton Roads | stip | project | 115377 | Urban | Norfolk | Traffic Management/Engineering | 455 | 0 | 0 | 455 | 2026-01-06 | Traffic Signal System Communications Network Upgrades | Various | Various | U000 | Various | 0 | 0.19 |  |  | 250000 |  | 1303992 | 1553992 | 1553992 | 2025-10-17 | 2026-09-17 |  |  | 2026-09-17 | 2028-02-04 | 1553992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Locally | No
Hampton Roads |  |  | 115378 | Public Transportation | Suffolk Transit | Transit | [5 empty] | Suffolk Transit Operatings Facility | [8 empty] | 2925000 | 0 | 0 | 2925000 |  | 2025-02-19 | 2025-05-23 |  |  | 2025-05-23 | 2027-05-20 | 4302042 | [8 empty] | FO | WATA-DRPT | No
Hampton Roads | stip | project | 115379 | Urban | Norfolk | Preliminary Engineering | 1852 | 0 | 0 | 1852 | 2026-01-06 | Newtown Road Corridor Study | Curlew Drive | Baker Road | U000 | Newtown Road | 0 | 1.02 | 1.6900 | MI | 250000 |  |  | 250000 | 250000 | 2024-08-01: 2025-06-05; 2026-02-28: 2026-09-22 | 250000 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 200000 |  | Locally | No
Hampton Roads |  |  | 115421 | [17 empty] | 1890066 | 0 | 0 | 0 |  | 2026-10-01: 2025-05-22; 2029-03-31: 2027-05-19 | 1890066 | [8 empty] | FO | Suffolk Transit-DRPT | No
Hampton Roads | stip | project | 115423 | Urban | Chesapeake | Reconstruction W/ Added Capacity | 3043 | 0 | 0 | 3043 | 2025-11-05 | George Washington Highway Widening | Yadkin Road | Canal Drive | 0017 | George Washington Highway | 22.56 | 24.06 | 1.5000 | MI | 3887873 | 8722936 | 47502983 | 60113792 | 60113792 | 2023-10-27 | 2026-06-05 | 2026-06-05 | 2027-04-06 | 2027-04-06 | 2029-07-18 | 54592292 | 0 | 0 | 0 | 0 | 2800000 | 0 | 0 | 2800000 | NFO | Locally | Yes
Hampton Roads | stip | project | 115424 | Urban | Norfolk | Facilities For Pedestrians And Bicycles | 1747 | 0 | 0 | 1747 | 2026-01-06 | Southside Bike Lane Network | Various | Various | U000 | Various | 0 | 0.19 | 3.4000 | MI | 124020 |  | 891880 | 1015900 | 1015900 | 2025-05-30 | 2026-06-30 |  |  | 2026-06-30 | 2027-06-17 | 1015900 | 0 | 0 | 0 | 0 | 83200 | 0 | 0 | 83200 |  | Locally | No
Hampton Roads |  |  | 115425 | Public Transportation | Williamsburg Area Transit Authority | Transit | [5 empty] | Strategic and Comprehensive Operating Anaylsis Study | [8 empty] | 300000 | 0 | 0 | 300000 |  | 2024-08-01: 2025-01-03; 2026-02-28: 2026-07-24 | 300000 | [8 empty] | FO | WATA-DRPT | No
Hampton Roads | stip | project | 115512 | Urban | James City County | Facilities For Pedestrians And Bicycles | 968307 | 4993 | 0 | 973300 | 2026-01-06 | #SMART20 Longhill Road Shared Use Path | Lane Place Drive | Charing Cross | U000 | Longhill Road | 3.37 | 2.78 | 0.4890 |  | 1005264 | 594865 | 5840699 | 7440828 | 7301934 | 2019-12-02 | 2025-10-31 | 2025-10-31 | 2026-06-09 | 2026-06-09 | 2027-09-30 | 7440828 | 0 | 0 | 0 | 0 | 695000 | 0 | 0 | 695000 |  | VDOT | No
Hampton Roads | stip | project | 115516 | Urban | Chesapeake | Reconstruction W/ Added Capacity | 180 | 0 | 0 | 180 | 2026-01-06 | Battlefield Blvd/Volvo Parkway Intersection Improvements | Intersection of Volvo Pkway & Battlefield Blvd | Intersection of Volvo Pkway & Battlefield Blvd | U000 | Volvo Parkway | 13.65 | 13.75 |  |  | 127500 | 190000 | 553173 | 870673 | 870673 | 2025-05-29 | 2026-08-04 | 2026-08-04 | 2027-07-02 | 2027-07-02 | 2028-11-14 | 870673 | 0 | 0 | 0 | 0 | 102000 | 0 | 0 | 102000 | NFO | Locally | No
Hampton Roads | stip | project | 115518 | Urban | Norfolk | Traffic Management/Engineering | 1205 | 0 | 0 | 1205 | 2026-01-06 | Citywide Signal Retiming Phase 4 | Various | Various | U000 | Various | 0 | 0.19 |  |  | 340000 |  |  | 340000 | 340000 | 2024-08-01: 2025-06-24; 2026-02-28: 2026-10-01 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 136000 | 136000 |  | Locally | No
Hampton Roads | stip | project | 115519 | Urban | Newport News | Traffic Management/Engineering | [5 empty] | Signal Retiming Improvements | Various | Various | U000 | Jefferson Ave | 0 | 0.445 |  | MI | 1350000 |  |  | 1350000 | 1350000 | 2024-08-01: 2025-12-04; 2026-02-28: 2027-05-25 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Locally | No
Hampton Roads | stip | project | 115520 | Urban | Chesapeake | Traffic Management/Engineering | 523 | 0 | 0 | 523 | 2026-01-06 | Chesapeake Signal Timing-All Phases (Study Only) | Various | Various | U000 | Various | 6.08 | 6.08 | 0.0000 | MI | 600000 |  |  | 600000 | 600000 | 2024-08-01: 2025-08-25; 2026-02-28: 2027-02-22 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 240000 | NFO | Locally | No
Hampton Roads | stip | project | 115525 | Urban | Suffolk | Facilities For Pedestrians And Bicycles | 328036 | 0 | 0 | 328036 | 2026-01-06 | #SMART20 Seaboard Coastline Trail Segment 1 | Moore Avenue | Suburban Drive | U000 | Various | 3.69 | 4.45 | 1.5000 | MI | 440150 | 103874 | 4720046 | 5264070 | 5264070 | 2023-07-11 | 2026-02-11 | 2026-02-11 | 2027-04-12 | 2027-04-12 | 2028-07-28 | 5264070 | 0 | 0 | 4720046 | 4720046 | 355949 | 0 | 0 | 355949 |  | Locally | Yes
Hampton Roads | stip | project | 115543 | Urban | Virginia Beach | New Construction Roadway | [5 empty] | Nimmo Parkway Phase VIIB | Albuquerque Drive | Western terminus of Sandbridge Road | U000 | Nimmo Parkway | 0.699 | 1.92 | 1.6000 | MI | 8234500 | 4608700 | 61873135 | 74716335 | 64913065 | 2026-09-25 | 2027-07-26 | 2027-07-26 | 2031-08-29 | 2031-08-29 | 2034-08-31 | 42000000 | 0 | 0 | 0 | 0 |  |  |  |  | NFO | Locally | Yes
Hampton Roads | stip | project | 115863 | Urban | Portsmouth | Traffic Management/Engineering | [5 empty] | Portsmouth Signal Timing - Phases 1-4 | Various | Various | U000 | Various | 0.41 | 0.41 |  |  | 480000 |  |  | 480000 | 480000 | 2024-08-01: 2026-02-13; 2026-02-28: 2027-08-11 | 480000 | 0 | 0 | 0 | 0 | [5 empty] | Locally | No
Hampton Roads | stip | project | 117038 | Enhancement | Norfolk | Facilities For Pedestrians And Bicycles | 63378 | 0 | 232684 | 296062 | 2025-11-07 | Church Street Pedestrian Improvements | Onley Avenue | Nicholson Street | EN20 | Church Street | 0.71 | 0.94 |  |  | 76332 |  | 289656 | 365988 | 365988 | 2021-08-30 | 2023-06-30 |  |  | 2023-06-30 | 2024-06-04 | 365988 | 0 | 0 | 0 | 0 | 61065.2 | 0 | 231724.98 | 292790.18 |  | Locally | No
Hampton Roads | stip | project | 118375 | Primary | Suffolk | Safety | 4228191 | 532359 | 22480256 | 27240805 | 2026-01-20 | SPSA Interchange Improvement | 0.429 Miles East of US 13/58/460 | 2.536 Miles West of Suffolk City Limits | 0058 | 000 | 476.2 | 476.33 | 1.1180 | MI | 5300000 | 2482570 | 38739817 | 46522387 | 46522387 | 2021-09-24 | 2023-04-04 | 2023-04-04 | 2024-03-12 | 2024-03-12 | 2026-07-24 | 46522387 | 0 | 0 | 0 | 0 | [5 empty] | VDOT | Yes
Hampton Roads | stip | project | 118376 | Interstate | Multi-jurisdictional: Hampton Roads MPO | Reconstruction W/ Added Capacity | 2472099 | 0 | 716 | 2472816 | 2026-01-06 | Hampton Roads Express Lanes - Segment 3 | 0.808 miles west of Mallory St. Interchange | 0.174 miles west of Tidewater Dr. Interchange | 0064 |  | 266.75 | 277.31 | 10.4210 | MI | 2531000 |  | 30995139 | 33526139 | 22789474 | 2022-09-29 | 2025-08-12 |  |  | 2025-08-12 | 2027-08-26 | 33526139 | 0 | 0 | 0 | 0 | [5 empty] | VDOT | Yes
Hampton Roads | stip | project | 118380 | Primary | Multi-jurisdictional: Hampton Roads MPO | Safety | 241386 | 0 | 1604229 | 1845615 | 2025-03-03 | Safety Improvements on Route 258 | Eastbound Rte. 58 Ramp | Amber Street | 0258 | South Street | 447.56 | 448.11 | 0.5500 | MI | 241386 | 0 | 1593739 | 1835125 | 1835125 | 2021-06-01 | 2022-06-09 | 2022-06-09 | 2023-02-14 | 2023-02-14 | 2024-07-06 | 2028866 | 0 | 0 | 0 | 0 | 193108.48 | 0 | 1363094 | 1556202.48 |  | VDOT | No
Hampton Roads | stip | project | 118642 | Urban | Norfolk | Reconstruction W/O Added Capacity | 35714 | 0 | 1107390 | 1143104 | 2026-01-06 | St. Paul's Roadway Improvements - Phase 2 | Fenchurch Street | South of Brambleton | 8575 | Fenchurch Street | 0 | 2.2 |  | MI | 71428 |  | 61725908 | 61797336 | 61797336 | 2023-03-14 | 2023-12-29 |  |  | 2023-12-29 | 2026-12-03 | 62643118 | 0 | 0 | 0 | 0 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119182 | Primary | Gloucester County | Other | [5 empty] | RT 17 WIDENING - SHORT LN TO MAIN ST (BUS) - STUDY ONLY | BURLEIGH/SHORT | MAIN STREET INTERSECTION | 0017 | GEORGE WASHINGTON MEM HIGHWAY | 79.4 | 80.48 | 1.1000 | MI | 250000 |  |  | 250000 | 250000 | 2024-08-01: 2026-08-21; 2026-02-28: 2029-12-03 | 250000 | 0 | 0 | 0 | 0 | [5 empty] | VDOT | No
Hampton Roads | stip | project | 119217 | Interstate | Newport News | Reconstruction W/ Added Capacity | 3382696 | 1862677 | 1870594 | 7115967 | 2026-01-16 | #SMART22 #SGRVB I-64 DENBIGH BOULEVARD INTERCHANGE | 0.393 Mi. North of Rte 173 (Denbigh Blvd) | 0.405 Mi. South of Rte 173 (Denbigh Blvd) | 0064 | Interstate 64 | 254.14 | 253.74 | 0.7980 | MI | 4066292 | 15234000 | 74119809 | 93420101 | 93420101 | 2022-08-31 | 2025-05-02 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 2029-06-28 | 93420101 | 0 | 385525 | 72070883 | 72456408 | 365237 | 0 | 0 | 365237 | FO | VDOT | Yes
Hampton Roads | stip | project | 119219 | Urban | Chesapeake | Facilities For Pedestrians And Bicycles | 1486 | 0 | 0 | 1486 | 2026-01-06 | #SMART22 WESTERN BRANCH RAILS TO TRAILS PHASE 2 | Gum Road | Taylor Rd. | U000 | Bruce Road | 2.09 | 2.45 |  |  | 464466 | 264365 | 1846897 | 2575728 | 2575728 | 2024-10-31 | 2026-03-03 | 2026-03-03 | 2026-11-25 | 2026-11-25 | 2027-11-10 | 2575728 | 0 | 0 | 1846897 | 1846897 | 0 | 0 | 0 | 0 |  | Locally | No
Hampton Roads | stip | project | 119222 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | [5 empty] | #SMART22 HOLLAND ROAD PHASE 1 | S Independence Blvd | S Plaza Trl | U000 | Holland Road | 6.28 | 6.86 | 0.5700 | MI | 3411683 | 6692223 | 14406579 | 24510485 | 24510485 | 2026-01-23 | 2028-04-21 | 2028-04-21 | 2029-01-12 | 2029-01-12 | 2029-12-31 | 24510485 | 0 | 6692223 | 14406579 | 21098802 | 0 | 0 | 0 | 0 |  | Locally | Yes
Hampton Roads | stip | project | 119230 | Urban | Suffolk | Facilities For Pedestrians And Bicycles | 237226 | 0 | 0 | 237226 | 2026-01-06 | #SMART22 SUFFOLK SEABOARD COASTLINE TRAIL - PHASE IIIA | Driver Lane | Nansemond River High School | U000 | Driver trailhead to Nansemond River High School | 8.36 | 10.44 | 1.7500 | MI | 345200 | 25000 | 1967664 | 2337864 | 2337864 | 2023-12-15 | 2026-02-11 | 2026-02-11 | 2027-04-12 | 2027-04-12 | 2028-07-31 | 3452238 | 0 | 0 | 1967664 | 1967664 | 0 | 0 | 0 | 0 |  | Locally | No
Hampton Roads | stip | project | 119264 | Urban | Chesapeake | Traffic Management/Engineering | [5 empty] | DEEP CREEK ELEMENTARY SCHOOL TRAFFIC SIGNAL IMPROVEMENT | Forehand Drive/Margaret Booker Drive | Forehand Drive/Margaret Booker Drive | U000 | George Washington Hwy | 20.98 | 21.98 | 0.0100 | MI | 185000 | 185000 | 2220000 | 2590000 | 2590000 | 2027-06-03 | 2029-08-30 | 2029-08-30 |  | 2030-06-07 | 2031-06-11 | 2100000 | 148000 | 148000 | 0 | 296000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119265 | Urban | Virginia Beach | Reconstruction W/O Added Capacity | [5 empty] | HOLLAND ROAD PHASE II | S Plaza Trail | Rosemont Rd | U000 | Holland Road | 5.08 | 6.4 | 1.3200 | MI | 318030 | 190235 | 1551549 | 2059814 | 2059814 | 2026-06-30 | 2028-08-22 | 2028-08-22 | 2030-04-01 | 2030-04-01 | 2031-04-01 | 2031224 | 0 | 152188 | 0 | 152188 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119266 | Urban | Suffolk | Reconstruction W/ Added Capacity | [5 empty] | CONSTANCE ROAD AT WILROY ROAD INTERSECTION | Constance Road/ Wilroy Road | Constance Road/Wilroy Road | U000 | Constance Road | 0.9 | 0.91 | 0.0100 | MI | 300000 | 2200000 | 400000 | 2900000 | 2900000 | 2026-06-26 | 2028-08-18 | 2028-08-18 | 2029-05-11 | 2029-05-11 | 2030-04-29 | 3200000 | 0 | 1760000 | 320000 | 2080000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119268 | Urban | Portsmouth | Traffic Management/Engineering | [5 empty] | CITYWIDE TRAFFIC SIGNAL SYSTEM UPGRADES | Various | Various | U000 |  | 25.02 | 32.39 |  |  | 100000 |  | 900000 | 1000000 | 1000000 | 2028-04-25 | 2030-09-10 |  |  | 2030-09-10 | 2031-08-27 | 1225000 | 80000 | 0 | 720000 | 800000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119269 | Urban | Chesapeake | Traffic Management/Engineering | [5 empty] | CENTERVILLE TURNPIKE/ELBOW ROAD INTERSECTION IMPROVEMENTS | Centerville Turnpike/Elbow Road Intersection | Centerville Turnpike/Elbow Road Intersection | U000 | Centerville Turnpike/ElbowRoad | 8.25 | 8.35 | 0.0100 | MI | 380000 | 1250000 | 4360000 | 5990000 | 5990000 | 2026-11-24 | 2029-03-06 | 2029-03-06 | 2029-12-06 | 2029-12-06 | 2030-11-25 | 4850000 | 304000 | 1000000 | 0 | 1304000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119270 | Urban | Chesapeake | Reconstruction W/ Added Capacity | [5 empty] | BATTLEFIELD BLVD AND JOHNSTOWN RD INTERSECTION IMPROVEMENTS | Battlefield Blvd/Johnstown Rd | Battlefield Blvd/Johnstown Rd | U000 | Battlefield Blvd/Johnstown Rd | 11.26 | 11.49 | 0.0100 | MI | 555000 | 741000 | 1377156 | 2673156 | 2673156 | 2027-05-31 | 2029-07-23 | 2029-07-23 | 2030-04-15 | 2030-04-15 | 2031-04-01 | 1377156 | 444000 | 592800 | 0 | 1036800 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119271 | Urban | Chesapeake | Traffic Management/Engineering | [5 empty] | RTE 460/58/13 SAFETY IMPROVEMENTS | US Routes 460/58/13 | US Routes 460/58/13 | U000 | US Routes 460/58/13 | 481.44 | 481.49 | 0.0100 | MI | 1608800 | 2750000 | 9827304 | 14186104 | 14186104 | 2027-05-31 | 2029-07-23 | 2029-07-23 | 2030-04-15 | 2030-04-15 | 2031-04-01 | 14186104 | 1287040 | 2200000 | 7861843 | 11348883 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119275 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | [5 empty] | LASKIN ROAD PHASE III | west of Phillips Ave. | Republic Rd | U000 | LASKIN ROAD | 506.8 | 507.51 | 0.7000 | MI | 3669000 | 9367604 | 18466550 | 31503154 | 31503154 | 2026-07-02 | 2030-01-25 | 2030-01-25 |  | 2030-12-18 | 2032-08-25 | 31503154 | 353480 | 7494083 | 0 | 7847563 | [5 empty] | Locally | Yes
Hampton Roads | stip | project | 119276 | Urban | Norfolk | Bridge Rehab W/O Added Capacity | [5 empty] | BRAMBLETON AVENUE BRIDGE REHABILITATION | 2nd Street | Boteourt Street | U000 | Branbleton | 28.04 | 28.17 | 0.1230 | MI | 0 |  | 4000000 | 4000000 | 4000000 | 2026-11-02 | 2029-03-19 |  |  | 2029-03-19 | 2030-03-05 | 4000000 | 0 | 0 | 3200000 | 3200000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119279 | Urban | York County | Other | [5 empty] | YORK COUNTY ROADWAY NEEDS ASSESSMENT | Main Street | Alexander Hamilton Blvd | U000 | Ballard Street | 0 | 258.45 |  |  | 600000 |  |  | 600000 | 600000 | 2024-08-01: 2027-02-01; 2026-02-28: 2029-05-22 | 600000 | 480000 | 0 | 0 | 480000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119280 | Urban | Virginia Beach | Traffic Management/Engineering | [5 empty] | VIRGINIA BEACH TRAFFIC SIGNAL SYSTEM RETIMING | Various | Various | U000 | Various | 51.64 | 51.64 |  |  | 663000 |  |  | 663000 | 663000 | 2024-08-01: 2026-07-01; 2026-02-28: 2028-10-19 | 663000 | 0 | 0 | 0 | 0 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119281 | Urban | York County | Facilities For Pedestrians And Bicycles | 68434 | 0 | 0 | 68434 | 2026-01-08 | VICTORY BOULEVARD SHARED USE PATH | Big Bethel Road | 0.024 Miles East of Sinclair Lane | 0171 |  | 3.8 | 4.77 | 0.9700 | MI | 867397 | 608093 | 2411328 | 3886818 | 3886818 | 2025-09-30 | 2026-12-21 | 2026-12-21 | 2027-09-14 | 2027-09-14 | 2028-08-31 | 3886818 | 0 | 486474 | 1929062 | 2415536 | 693918 | 0 | 0 | 693918 |  | VDOT | No
Hampton Roads | stip | project | 119334 | Urban | Suffolk | Reconstruction W/ Added Capacity | 1192389 | 0 | 0 | 1192389 | 2026-01-09 | #SMART22 GODWIN BOULEVARD IMPROVEMENTS | Suffolk Bypass (US 460/58/13) | Hillpoint Blvd. | U000 | Godwin Blvd. | 15.89 | 16.89 | 1.5000 | MI | 1375000 | 1755564 | 12986980 | 16117544 | 16117544 | 2023-03-14 | 2026-09-17 | 2026-09-17 | 2027-09-15 | 2027-09-15 | 2030-05-15 | 16117544 | 361999 | 1755564 | 12986980 | 15104543 | 1013001 | 0 | 0 | 1013001 |  | Locally | Yes
Hampton Roads | stip | project | 119378 | Urban | Suffolk | Reconstruction W/ Added Capacity | [5 empty] | WILROY ROAD AT PROGRESS ROAD INTERSECTION | Wilroy Road/ Progress Road Intersection | Wilroy Road/Progress Road Intersection | U000 | Wilroy Road | 2.66 | 2.67 | 0.0100 | MI | 300000 | 1800000 | 400000 | 2500000 | 2500000 | 2026-06-30 | 2028-09-27 | 2028-09-27 |  | 2029-07-05 | 2030-07-09 | 2500000 | 0 | 1440000 | 320000 | 1760000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119409 | Urban | Chesapeake | Traffic Management/Engineering | 104433 |  |  |  |  | CHESAPEAKE SIGNAL TIMING - PHASES 1-4 (Study Only) | Military Highway | Kempville Road | U000 | Citywide locations | 6.07 | 6.09 | 0.0200 | MI | 600000 |  |  | 600000 | 600000 | 2024-08-01: 2027-09-29; 2026-02-28: 2030-01-28 | 600000 | 480000 | 0 | 0 | 480000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 119637 | Interstate | Norfolk | Reconstruction W/ Added Capacity | 2671455 | 38864 | 43156233 | 45866551 | 2026-01-14 | HAMPTON ROADS EXPRESS LANES, SEGMENT 1A | 0.078 miles east of Patrol Road | 0.558 miles east of Tidewater Drive | 0064 | I-64 | 275.7 | 284.5 | 2.2000 | MI | 2918320 | 500000 | 88661245 | 92079565 | 92079565 | 2022-05-03 | 2022-12-13 | 2022-12-13 | 2022-12-14 | 2022-12-14 | 2026-01-15 | 92079565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 119638 | Interstate | Hampton | Bridge Replacement W/ Added Capacity |  | 1702183 | 276367413 | 278174029 | 2026-01-20 | HAMPTON ROADS EXPRESS LANES, SEGMENT 4C | 0.136 Mi. East of LaSalle Ave. | 0.398 Mi. East of Settlers Landing Rd | 0064 | I-64 | 265.5 | 268 | 2.4150 | MI | 104433 | 8000000 | 391048878 | 399153311 | 399153311 | 2022-02-15 | 2022-06-24 | 2022-06-24 | 2022-06-27 | 2022-06-27 | 2026-12-30 | 399153311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 119824 | Interstate | Newport News | Reconstruction W/ Added Capacity | 3404674 | 43639 | 60732704 | 64181016 | 2026-01-14 | HAMPTON ROADS EXPRESS LANE, SEGMENT 4A-4B | 1.200 Mi. West of Denbigh Blvd | 0.139 Mi. East of LaSalle Avenue | 0064 | I-64 | 252 | 265.5 | 13.3870 | MI | 4874638 | 77782 | 131659074 | 136611494 | 136611494 | 2022-05-02 | 2023-01-19 | 2023-01-19 | 2023-11-21 | 2023-11-21 | 2027-07-19 | 136611494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 120375 | Interstate | Chesapeake | Reconstruction W/ Added Capacity | 2541654 | 2601 | 39879286 | 42423540 | 2026-01-20 | #I64CIP I-64/I-464 Interchange Exit 291 Ramp Improvements | 0.199 Mi. West of Intersection of I-464 SBL | 1.821 Mi. East of Intersection of I-464 SBL | 0064 | Hampton Roads Beltway | 290.1 | 292.1 | 2.0200 | MI | 4420000 | 1685720 | 133894280 | 140000000 | 140000000 | 2022-01-21 | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2027-11-03 | 140000000 | 0 | 0 | 10570621 | 10570621 | 4420000 | 1685720 | 97721411 | 103827131 |  | VDOT | Yes
Hampton Roads | stip | project | 120649 | Primary | Suffolk | Reconstruction W/ Added Capacity | 1043980 | 0 | 0 | 1043980 | 2026-01-06 | ROUTE 17 (BRIDGE ROAD) ROADWAY WIDENING | Windward Lane | Harbour View Blvd. | 0017 | Route 17 | 34.91 | 35.78 | 1.0000 | MI | 1930000 | 3894166 | 18371663 | 24195829 | 24195829 | 2022-12-30 | 2026-08-05 | 2026-08-05 | 2027-01-12 | 2027-01-12 | 2028-01-14 | 12796731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Locally | Yes
Hampton Roads | stip | project | 120650 | Primary | Isle of Wight County | Reconstruction W/ Added Capacity | 857184 | 161 | 0 | 857346 | 2026-01-15 | MAIN STREET (U.S. RTE 258) AT RTE 10 BYPASS | Main Street | Route 10 | 0258 | Main Street | 44.76 | 44.78 | 0.0000 | MI | 908000 | 286000 | 7568225 | 8762225 | 8762225 | 2023-04-11 | 2025-09-17 | 2025-09-17 | 2027-01-18 | 2027-01-18 | 2028-06-30 | 8762225 | 0 | 0 | 7568225 | 7568225 | 0 | 0 | 0 | 0 |  | Locally | No
Hampton Roads | stip | project | 120731 | Interstate | Norfolk | Bridge Rehab W/O Added Capacity | 0 | 0 | 13657034 | 13657034 | 2025-12-23 | #SS-WILLOUGHBY BAY BRIDGE- HRBT EXP - BR REPAIR WORK OPTION | 0.48mi from 4th View St | 0.57 mi to Hampton City line | 0064 | I-64 | 272.847 | 273.732 |  |  |  |  | 44721806 | 44721806 | 20638868 | 2026-10-01: 2022-03-10; 2029-03-31: 2027-08-27 | 44721806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | No
Hampton Roads | stip | project | 120863 | Interstate | Norfolk | Reconstruction W/ Added Capacity | 6474178 | 0 | 0 | 6474178 | 2026-01-06 | HAMPTON ROADS EXPRESS LANES, SEGMENT 1B | 0.558 miles East of Tidewater Drive | 0.977 miles East of I-264 | 0064 | I-64 | 278.3 | 285.1 | 7.0000 | MI | 6410180 | 500000 | 396903775 | 403813955 | 343687828 | 2022-05-26 | 2025-05-04 | 2025-05-04 | 2025-05-05 | 2025-05-05 | 2030-01-02 | 429839603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | program | 121052 | Interstate | Norfolk | Reconstruction W/ Added Capacity | 448672 | 0 | 0 | 448672 | 2026-01-06 | #BF #SGR VB - HREL SEGMENT 1B BRIDGE MAINTENANCE YEARS 2-5 | 0.661 miles East of Tidewater Drive | 1.04 miles East of I-264 | 0064 | I-64 |  |  |  |  | 1000000 |  | 57565929 | 58565929 | 56600000 | 2022-05-26 | 2025-05-05 |  |  | 2025-05-21 | 2030-02-15 | 58565929 | 0 | 0 | 0 | 0 | 1000000 | 0 | 34000000 | 35000000 |  | VDOT | Yes
Hampton Roads | stip | program | 121054 | Interstate | Newport News | Reconstruction W/ Added Capacity | 186466 | 0 | 8038205 | 8224672 | 2026-01-08 | #BF - HREL SEGMENT 4A-4B BRIDGE MAINTENANCE YEARS 2-5 | 1.2 Miles West of Denbigh Blvd | 0.139 Miles East of LaSalle Avenue | 0064 | I-64 |  |  |  |  | 186466 |  | 19298247 | 19484713 | 19484713 | 2022-05-02 | 2023-11-21 |  |  | 2023-11-21 | 2026-05-11 | 19484713 | 0 | 0 | 0 | 0 | 186466.23 | 0 | 16984712 | 17171178.23 |  | VDOT | Yes
Hampton Roads |  |  | 121098 | Urban | Virginia Beach | Reconstruction W/ Added Capacity | [5 empty] | Pungo Ferry Road Improvements | Blackwater Road | West side of the Pungo Ferry Road bridge Approach |  | Pungo Ferry Road |  |  | 2.0 | MI | 1415000 | 269000 | 34416800 | 36100800 |  | 2024-12-01 | 2029-06-30 | 2024-12-01 | 2029-12-31 | 2030-08-01 | 2034-06-30 | 36100800 | [8 empty] | NFO | Locality | No
Hampton Roads | stip | project | 121101 | Urban | Suffolk | Reconstruction W/ Added Capacity | 520 | 0 | 0 | 520 | 2026-01-06 | SHOULDER'S HILL ROAD WIDENING, 2-4 LANES PHASE 3 | Bennett's Creek Park Road | Pughsville Road | U000 | Shoulder's Hill Road | 1.413 | 2.165 | 0.7500 | MI | 1104862 | 2345513 | 9750519 | 13200894 | 13200894 | 2024-11-21 | 2026-06-01 | 2026-06-01 | 2027-12-01 | 2027-12-01 | 2029-07-12 | 13200894 | 0 | 0 | 4875259 | 4875259 | [5 empty] | Locally | Yes
Hampton Roads | stip | project | 121102 | Urban | Suffolk | Reconstruction W/ Added Capacity | 941 | 0 | 0 | 941 | 2025-11-05 | SHOULDER'S HILL ROAD WIDENING, 2-4 LANES PHASE 2 | Laycock Lane | Bennett's Creek Park Road | U000 | Shoulder's Hill Road | 2.16 | 2.766 | 0.6500 | MI | 772800 | 285547 | 7379209 | 8437556 | 8437556 | 2024-11-21 | 2026-06-01 | 2026-06-01 | 2027-12-01 | 2027-12-01 | 2028-11-16 | 8437556 | 0 | 0 | 3689604 | 3689604 | [5 empty] | Locally | Yes
Hampton Roads | stip | project | 121104 | Enhancement | Chesapeake | Facilities For Pedestrians And Bicycles | 23327 | 0 | 123 | 23450 | 2026-01-06 | CHESAPEAKE TRAIL PH2- DORDON TO TAYLOR | Dordon Street | Taylor Road | EN22 | Chesapeake Trail | 2.22 | 3.13 | 2.6000 | MI | 25000 | 0 | 1132970 | 1157970 | 1067190 | 2022-12-21 | 2024-07-26 | 2024-07-26 | 2025-04-11 | 2025-04-11 | 2026-07-01 | 1157970 | 0 | 0 | 0 | 0 | 50482.4 | 0 | 532462 | 582944.4 |  | Locally | No
Hampton Roads | stip | project | 121107 | Enhancement | Chesapeake | Facilities For Pedestrians And Bicycles | 20357 | 0 | 0 | 20357 | 2026-01-06 | CHESAPEAKE TRAIL PH3 - TAYLOR TO SUFFOLK |  | Taylor Road | EN22 | Chesapeake Trail | 0 | 2.45 | 1.0000 | MI | 220861 | 288013 | 2101408 | 2610282 | 2610282 | 2022-12-12 | 2026-02-06 | 2026-02-06 | 2026-06-25 | 2026-06-25 | 2027-06-11 | 2610282 | 0 | 0 | 0 | 0 | 176689 | 0 | 0 | 176689 |  | Locally | No
Hampton Roads | stip | project | 121108 | Enhancement | Newport News | Facilities For Pedestrians And Bicycles | 162686 | 0 | 0 | 162686 | 2026-01-06 | BOAT TRAIL MUP YORKTOWN RD TO NEWPORT NEWS PARK | Existing Bike Trail in Newport News Park | Chelsea Place & Yorktown Rd | EN22 |  | 0.528 | 1.466 |  |  | 678000 | 246000 | 3367000 | 4291000 | 4291000 | 2023-10-19 | 2026-08-31 | 2026-08-31 | 2027-06-30 | 2027-06-30 | 2028-09-28 | 4291000 | 0 | 196800 | 3301800 | 3498600 | 542400 | 0 | 0 | 542400 |  | Locally | No
Hampton Roads | stip | project | 121109 | Enhancement | Suffolk | Preservation Of Abandoned Railway Corridors | 135565 | 0 | 0 | 135565 | 2026-01-06 | SEABOARD COASTLINE TRAIL PHASE 3B | Nansemond Parkway | Pine Tree Way/Cherry Blossom Dr | EN22 | Seaboard Coastline Trail | 4.936 | 6.378 | 1.5000 | MI | 460048 | 83000 | 1770200 | 2313248 | 2313248 | 2023-03-14 | 2025-11-05 | 2025-11-05 | 2027-04-12 | 2027-04-12 | 2028-07-28 | 2270200 | 0 | 0 | 0 | 0 | 368038 | 0 | 0 | 368038 |  | Locally | No
Hampton Roads | stip | project | 121110 | Enhancement | Newport News | Facilities For Pedestrians And Bicycles | 119429 | 0 | 0 | 119429 | 2026-01-06 | BOAT MUP WARWICK, ELMHURST, & YORKTOWN | Existing Bike Trail in Newport News Park | Chelsea Place & Yorktown Road | EN22 |  | 249.402 | 250.011 |  |  | 490000 | 574000 | 2029000 | 3093000 | 3093000 | 2023-10-17 | 2026-08-31 | 2026-08-31 | 2027-06-30 | 2027-06-30 | 2028-09-28 | 3093000 | 0 | 0 | 0 | 0 | 392000 | 0 | 0 | 392000 |  | Locally | No
Hampton Roads | stip | program | 121360 | Interstate | Norfolk | Reconstruction W/ Added Capacity | 0 | 0 | 85068097 | 85068097 | 2025-11-21 | HAMPTON ROADS EXPRESS LANES, SEGMENT 1A (CN Phase Only) | 0.15 miles east of Patrol Bridge Road | 0.663 miles east of Tidewater Drive | 0064 | I-64 | [6 empty] | 85068097 | 85068097 | 85068097 | 2026-10-01: 2024-07-26; 2029-03-31: 2026-03-27 | 85068097 | 0 | 0 | 0 | 0 | 0 | 0 | 54887868.18 | 54887868.18 |  | VDOT | Yes
Hampton Roads | stip | program | 121361 | Interstate | Norfolk | Reconstruction W/ Added Capacity | 0 | 0 | 8031903 | 8031903 | 2025-04-30 | HAMPTON ROADS EXPRESS LANES, SEGMENT 1A (CN Phase Only) | 0.15 miles east of Patrol Bridge Road | 0.663 miles east of Tidewater Drive | 0064 | I-64 | [6 empty] | 8031903 | 8031903 | 8031903 | 2026-10-01: 2024-07-26; 2029-03-31: 2026-03-27 | 8031903 | 0 | 0 | 0 | 0 | 0 | 0 | 6911474.91 | 6911474.91 |  | VDOT | Yes
Hampton Roads | stip | project | 122714 | Interstate | Chesapeake | Other | 1620879 | 0 | 0 | 1620879 | 2025-12-08 | I-464/I-64 INTERCHANGE ACCESS REPORT (IAR) | I464/I64 | I464/I64 | 0464 | I464 | 0.046 | 0.046 |  |  | 2500000 |  |  | 2500000 | 2500000 | 2024-08-01: 2023-01-11; 2026-02-28: 2026-06-03 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 122761 | Interstate | Virginia Beach | Other | 862102 | 0 | 0 | 862102 | 2026-01-06 | I-264/INDEPENDENCE BLVD INTERCHANGE IMPROVEMENT(IAR) | I264-Independence Blvd Interchange | I264 Witchduck Road Interchange | 0264 | I-264 | 14.96 | 16.64 |  |  | 1250000 |  |  | 1250000 | 1250000 | 2024-08-01: 2023-04-20; 2026-02-28: 2025-08-11 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 123055 | Urban | York County | Facilities For Pedestrians And Bicycles | [5 empty] | #SMART24 BOAT TRAIL - HAMPTON HIGHWAY SEGMENT | Hampton Hwy | Hampton Hwy | 0134 | Hampton Highway | 0.39 | 0.98 |  |  | 716459 | 1662206 | 3175173 | 5553838 | 5553838 | 2027-03-29 | 2029-07-05 | 2029-07-05 | 2030-04-09 | 2030-04-09 | 2031-03-26 | 5553838 | 716459 | 1662206 | 3175173 | 5553838 | [5 empty] | VDOT | No
Hampton Roads | stip | project | 123129 | Interstate | James City County | Reconstruction W/ Added Capacity | 1619638 | 0 | 97479307 | 99098944 | 2026-01-16 | #SMART24 - I-64 GAP WIDENING - SEGMENT C | NEW KENT/JAMES CITY COUNTY LINE | 1.15 MILES WEST OF ROUTE 199 (EXIT 234) | 0064 | I-64 | 224.3 | 233.3 | 9.0000 | MI | 1619638 | 100000 | 204348858 | 206068496 | 206068496 | 2023-07-20 | 2023-10-17 | 2023-10-17 | 2023-11-07 | 2023-11-07 | 2027-11-19 | 229265701 | 0 | 0 | 0 | 0 | 4500000 | 100000 | 45020154 | 49620154 |  | VDOT | Yes
Hampton Roads | stip | project | 123154 | Urban | Norfolk | New Construction Roadway | 2415609 | 0 | 0 | 2415609 | 2026-01-06 | AIR TERMINAL INTERCHANGE-INTERMODAL CONNECTOR EASTERN | I-564 | Hampton Blvd | 0564 |  | 1.52 | 2.27 |  |  | 6670000 | 2210000 | 100160000 | 109040000 | 109040000 | 2023-08-04 | 2027-07-27 | 2027-07-27 | 2028-06-15 | 2028-06-15 | 2033-11-11 | 6670000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 123160 | Urban | Newport News | Reconstruction W/ Added Capacity | [5 empty] | #SMART24 J.CLYDE MORRIS BOULEVARD WIDENING | Diligence Drive | Traverse Road | 0017 | J Clyde Morris Boulevard | 56.53 | 57.33 | 0.7970 | MI | 900188 | 783686 | 3386376 | 5070250 | 5070250 | 2025-12-19 | 2028-05-04 | 2028-05-04 | 2029-01-25 | 2029-01-25 | 2030-01-14 | 5070250 | 0 | 783686 | 3386376 | 4170062 | 0 | 0 | 0 | 0 |  | Locally | Yes
Hampton Roads | stip | project | 123166 | Urban | Norfolk | Reconstruction W/ Added Capacity | [5 empty] | #SMART24 VIRGINIA BEACH BLVD - GEORGE STREET TO WINBURNE LN | George Street | Winburne Lane | 0058 | Virginia Beach Boulevard | 497.35 | 497.68 |  |  | 855074 | 467490 | 7945261 | 9267825 | 9267825 | 2026-06-15 | 2028-08-07 | 2028-08-07 | 2029-04-30 | 2029-04-30 | 2030-04-16 | 9267825 | 0 | 467490 | 7945261 | 8412751 | [5 empty] | Locally | Yes
Hampton Roads | stip | project | 123179 | Urban | Newport News | Reconstruction W/ Added Capacity | [5 empty] | #SMART24 OYSTER POINT WIDENING II | Warick Boulevard (US 60) | Radcliff Lane | 1015 | Oyster Point Road | 0 | 0.36 | 0.3600 | MI | 1113119 | 3980472 | 6190918 | 11284509 | 11284509 | 2025-11-13 | 2028-05-04 | 2028-05-04 | 2029-01-25 | 2029-01-25 | 2030-01-11 | 11284509 | 1113119 | 3980472 | 6190918 | 11284509 | 0 | 0 | 0 | 0 |  | Locally | Yes
Hampton Roads | stip | program | 123322 | Interstate | Chesapeake | Reconstruction W/ Added Capacity | 0 | 0 | -1259 | -1259 | 2025-12-01 | I-64/464 INTERCHANGE EXIT 291 RAMP IMPROVEMENTS | 0.199 Mi. West of Intersection of I-464 SBL | 1.821 Mi. East of Intersection of I-464 SBL | 0064 | Hampton Roads Beltway |  |  | 2.0200 | MI |  |  | 15380374 | 15380374 | 0 | 2026-10-01: 2024-09-10; 2029-03-31: 2026-05-05 | 15380374 | 0 | 0 | -25482549 | -25482549 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 123585 | Urban | Virginia Beach | Reconstruction W/O Added Capacity | [5 empty] | LASKIN ROAD PHASE I-B | Red Robin Road | Oriole Drive | U000 | LASKIN ROAD | 508.49 | 509.06 | 0.6000 | MI | 4000000 | 1005000 | 54432039 | 59437039 | 59437039 | 2026-06-30 | 2027-09-01 | 2027-09-01 | 2032-10-01 | 2032-10-01 | 2036-11-03 | 59437039 | 0 | 1004000 | 0 | 1004000 | [5 empty] | Locally | Yes
Hampton Roads | stip | project | 123587 | Urban | Chesapeake | Traffic Management/Engineering | [5 empty] | 17/460 INTERSECTION IMPROVEMENT | Military Hwy/ George Washington Hwy. | Military Hwy/George Washington Hwy. | 0017 | Military Hwy/George Washington Hwy. | 23.25 | 23.25 | 1.0000 | MI | 1028444 | 1380686 | 9814153 | 12223283 | 12223283 | 2028-10-02 | 2030-11-25 | 2030-11-25 | 2031-08-18 | 2031-08-18 | 2032-08-03 | 2409126 | 822755 | 0 | 0 | 822755 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123588 | Urban | Norfolk | Traffic Management/Engineering | [5 empty] | CITYWIDE FIBER UPGRADES | St. Paul's Blvd | St. Paul's Blvd | U000 | Union Street (City Hall) | 399.88 | 399.9 |  |  | 307580 |  | 5690230 | 5997810 | 5997810 | 2028-10-02 | 2031-02-17 |  |  | 2031-02-17 | 2032-02-03 | 3721782 | 246064 | 0 | 0 | 246064 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123635 | Urban | Norfolk | Facilities For Pedestrians And Bicycles | [5 empty] | MILITARY HIGHWAY AT POPLAR HALL SHARED USE PATH | Poplar Hall | Piping Rock Road | 0264 | N. Military Hwy | 47.58 | 47.82 |  |  | 977959 | 2861604 | 5406296 | 9245859 | 9245859 | 2028-10-02 | 2030-11-25 | 2030-11-25 | 2031-08-18 | 2031-08-18 | 2032-08-03 | 4395433 | 782367 | 0 | 0 | 782367 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123636 | Urban | Chesapeake | Traffic Management/Engineering | [5 empty] | MILITARY HIGHWAY NEAR BAINBRIDGE BLVD SAFETY IMPROVEMENTS | Bainbridge Blvd. | Near Gilmerton Bridge | 0013 | Military Highway | 40.19 | 40.49 | 1.0000 |  | 300000 | 117000 | 1651188 | 2068188 | 2068188 | 2028-10-02 | 2030-11-25 | 2030-11-25 | 2031-08-18 | 2031-08-18 | 2032-08-03 | 417000 | 240000 | 0 | 0 | 240000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123637 | Urban | Chesapeake | Traffic Management/Engineering | [5 empty] | CENTERVILLE TURNPIKE WIDENING STUDY | Mt. Pleasant Road | Elbow Road | U000 | Centerville Turnpike Widening Study | 5.96 | 7.68 | 1.5000 | MI | 3254000 |  |  | 3254000 | 3254000 | 2024-08-01: 2028-10-02; 2026-02-28: 2030-12-17 | 3254000 | 2603200 | 0 | 0 | 2603200 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123638 | Urban | Norfolk | Preliminary Engineering | [5 empty] | DOWNTOWN NORFOLK MARKET STRT ST. PAUL'S COMPREHENSIVE STUDY | St Paul's Blvd | E. Main Street | 0264 | US-460 ALT E | 399.98 | 400 |  |  | 2500000 |  |  | 2500000 | 2500000 | 2024-08-01: 2028-10-02; 2026-02-28: 2030-12-17 | 2500000 | 2000000 | 0 | 0 | 2000000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123639 | Urban | Norfolk | Traffic Management/Engineering | [5 empty] | 26TH STREET/LAFAYETTE BOULEVARD LANE REPURPOSING | Tidewater Drive | Leo Street | 0247 | 26TH Street/Lafayette Boulevard | 1.45 | 2.4 |  |  | 316943 |  | 1791708 | 2108651 | 2108651 | 2028-10-02 | 2031-02-17 |  |  | 2031-02-17 | 2032-02-03 | 2108381 | 253554 | 0 | 0 | 253554 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123640 | Public Transportation | Suffolk | Other | [5 empty] | SUFFOLK TRANSIT BUS PRE-EMPTION | City of Suffolk | City of Suffolk | U000 |  | 0.57 | 0.57 | 0.0000 | MI | 2000 |  | 35800 | 37800 | 37800 | 2028-10-02 | 2030-09-16 |  |  | 2030-09-16 | 2031-09-02 | 37800 | 1600 | 0 | 0 | 1600 | [5 empty] | Locally | No
Hampton Roads |  |  | 123641 | Urban | Isle of Wight County | Reconstruction W/ Added Capacity | [5 empty] | Route 17 Widening Improvements at Smith Neck Road (PE and RW Only) | James River Bridge | Smith Neck Road | 0017 | Carrollton Blvd |  |  |  |  | 1184926 | 817958 |  | 2002884 |  | 2028-10-02 | 2032-02-23 | 2032-02-23 | 2033-01-03 |  |  | 2003000 | [8 empty] | NFO | VDOT | Yes
Hampton Roads | stip | project | 123642 | Urban | Chesapeake | Preliminary Engineering | [5 empty] | PLEASANT GROVE PARKWAY ALIGNMENT STUDY | Various | Various | U000 | Pleasant Grove Parkway | 6.06 | 6.08 | 0.0000 | MI | 2850000 |  |  | 2850000 | 2850000 | 2024-08-01: 2028-10-02; 2026-02-28: 2030-12-17 | 2850000 | 2280000 | 0 | 0 | 2280000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123656 | Interstate | Newport News | Reconstruction W/ Added Capacity | 2659374 | 0 | 0 | 2659374 | 2026-01-14 | I-64 DENBIGH BOULEVARD INTERCHANGE PHASE 2 - EB | 0.433 Mi. North of Rte 173 (Denbigh Blvd) | 0.619 Mi. South of Rte 173 (Denbigh Blvd) | 0064 | Interstate 64 | 253.41 | 253.95 | 1.0510 | MI | 17712000 | 8931026 | 161420044 | 188063070 | 188063070 | 2023-09-06 | 2026-12-08 | 2026-12-08 | 2030-04-09 | 2030-04-09 | 2034-08-03 | 26643026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 123750 | Urban | Virginia Beach | Traffic Management/Engineering | [5 empty] | CORRIDOR TRAFFIC SIGNAL RETIMING | Various | Various | U000 | Various | 0.39 | 0.39 |  |  | 960000 |  |  | 960000 | 960000 | 2024-08-01: 2029-01-25; 2026-02-28: 2031-04-11 | 960000 | 768000 | 0 | 0 | 768000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123764 | Urban | Newport News | Facilities For Pedestrians And Bicycles | [5 empty] | POCAHONTAS TR FROM GREEN MT PKWY WARWICK BLVD AT FALL REACH | Intersection of Green Mount Parkway and Pochontas Trail | Intersection of Warick Blvd and Falls Reach Pkwy | U000 | Multi Use Path | 247.94 | 249.41 | 1.4700 | MI | 1520000 | 778000 | 7580000 | 9878000 | 9878000 | 2028-11-27 | 2031-01-20 | 2031-01-20 | 2031-10-13 | 2031-10-13 | 2032-09-28 | 9878000 | 1216000 | 0 | 0 | 1216000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123765 | Urban | Suffolk | Other | [5 empty] | CITYWIDE TRAFFIC SIGNAL SYSTEM TIMING | Citywide | Various Locations | U000 |  | 0.59 | 0.59 | 0.0000 | MI | 300000 |  | 610000 | 910000 | 910000 | 2028-10-02 | 2031-02-17 |  |  | 2031-02-17 | 2032-02-03 | 910000 | 240000 | 0 | 0 | 240000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123766 | Urban | Norfolk | Traffic Management/Engineering | [5 empty] | CITYWIDE SIGNAL RETIMING PHASE V | Citywide | Citywide | U000 | Various | 400.12 | 400.14 |  |  | 680000 |  |  | 680000 | 680000 | 2024-08-01: 2029-02-23; 2026-02-28: 2031-05-12 | 680000 | 544000 | 0 | 0 | 544000 | [5 empty] | Locally | No
Hampton Roads | stip | project | 123832 | Primary | York County | Other | 89048 | 0 | 20261 | 109308 | 2025-10-14 | #SMART24 - I-64 GAP WIDENING - SEGMENT C - PARK AND RIDE | 0.9 miles northeast Mooretown Rd (SR 603) | 0.9 miles northeast Mooretown Rd (SR 603) | 0137 | E. Rochambeau Drive | 0.83 | 0.88 | 0.1000 | MI | 89048 |  | 1589779 | 1678827 | 1678827 | 2023-10-12 | 2023-10-23 |  |  | 2023-10-23 | 2027-11-19 | 2525891 | 0 | 0 | 0 | 0 | 200000 | 0 | 1589779 | 1789779 |  | VDOT | No
Hampton Roads | stip | program | 124309 | Miscellaneous | Statewide | Other | 16006307 | 0 | 0 | 16006307 | 2025-12-02 | Transforming Rail in Virginia - VRE Operations Costs / VPRA | DC Rte 46 and Rte 50 | Roanoke, Newport News, Norfolk and Richmond | AGBE |  |  |  | 0.0000 |  | 86496436 |  |  | 86496436 | 0 | 2024-08-01: 2022-04-26; 2026-02-28: 2024-04-26 | 86496436 | 14845207 | 0 | 0 | 14845207 | 54354792.95 | 0 | 0 | 54354792.95 |  | VPRA | Yes
Hampton Roads | stip | project | 125241 | Enhancement | York County | Facilities For Pedestrians And Bicycles | 67836 | 0 | 0 | 67836 | 2026-01-06 | Trail 757, York Sec 1 | Route 17 | Oriana Road | EN24 | Oriana Road | 0 | 6.87 |  |  | 338995 | 247786 | 1140674 | 1727455 | 1727455 | 2025-03-05 | 2027-02-05 | 2027-02-05 | 2029-03-01 | 2029-03-01 | 2030-02-15 | 2809241 | 0 | 198228 | 912539 | 1110767 | 387140 | 0 | 0 | 387140 |  | Locally | No
Hampton Roads | stip | project | 125243 | Enhancement | Suffolk | Facilities For Pedestrians And Bicycles | [5 empty] | SUFFOLK SEABOARD COASTLINE TRAIL - 3C | Nansemond River High School | Pine Tree Way-northern terminus of Segment 3B | EN24 |  | 5.77 | 8.47 | 2.7000 | MI | 737100 | 3572100 | 4139381 | 8448581 | 8448581 | 2026-01-22 | 2028-03-17 | 2028-03-17 | 2028-12-08 | 2028-12-08 | 2029-11-23 | 8448581 | 589680 | 2235320 | 4139381 | 6964381 | [5 empty] | Locally | No
Hampton Roads | stip | project | 125360 | Urban | Suffolk | Preliminary Engineering | 54 | 0 | 0 | 54 | 2025-06-03 | KING'S HIGHWAY BRIDGE REPLACEMENT (PE Only) | Route 125 | Route 10 | U000 | Kings Highway Bridge | 2.85 | 2.85 | 0.4500 | MI | 3800000 |  |  | 3800000 | 3800000 | 2024-08-01: 2025-04-17; 2026-02-28: 2027-04-13 | 3800000 | 0 | 0 | 0 | 0 | 3040000 | 0 | 0 | 3040000 |  | Locally | No
Hampton Roads | stip | project | 125602 | Interstate | Norfolk | Reconstruction W/ Added Capacity | 1787370 | 0 | 0 | 1787370 | 2026-01-20 | I-64/I-264 INTERCHANGE PHASE IIIA | 0.081 Miles South of Northampton Boulevard | 1.04 Miles East of I-264 | 0064 | I-264; I-64 |  |  |  |  | 3058998 | 1623000 | 512334002 | 517016000 | 517016000 | 2024-10-18 | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-11 | 2030-11-18 | 517016000 | 0 | 0 | 409701400 | 409701400 | [5 empty] | VDOT | Yes
Hampton Roads | stip | project | 125974 | Urban | Virginia Beach | Reconstruction W/O Added Capacity | 764 | 0 | 0 | 764 | 2026-01-12 | PACIFIC AVE AT 17th ST & PACIFIC AVE AT 22ND ST IMPROVEMENTS | 23rd Street | 15th Street | 0060 | Pacific Avenue | 302.57 | 303.18 | 0.6000 | MI | 3000000 | 0 | 0 | 3000000 | 3000000 | 2025-05-12 | 2029-02-14 | 2029-02-14 | 2029-12-26 | 2029-12-26 | 2031-08-07 | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 3000000 |  | Locally | No
Hampton Roads | stip | project | 125975 | Urban | Norfolk | Traffic Management/Engineering | 7760 | 0 | 0 | 7760 | 2026-01-08 | SIGNAL SYSTEM UPGRADE FOR INCIDENT MANAGEMENT | Union Street | Union Street | 0165 | St. Pauls Blvd | 0 | 35.85 |  |  | 377900 |  | 2622100 | 3000000 | 3000000 | 2025-05-30 | 2027-06-03 |  |  | 2027-06-03 | 2028-05-19 | 3000000 | 0 | 0 | 2622100 | 2622100 | 377900 | 0 | 0 | 377900 |  | Locally | No
Hampton Roads | stip | project | 126777 | Urban | Suffolk | Traffic Management/Engineering | [5 empty] | ROUTE 460 WIDENING | Route 460/Route 58 Interchange | Providence Road/Lake Prince Drive Intersection | 0460 | 460 | 371.8 | 373.72 | 2.1000 | MI | 8600000 | 30100000 | 48049520 | 86749520 | 86749520 | 2026-01-20 | 2029-03-28 | 2029-03-28 | 2030-02-06 | 2030-02-06 | 2031-09-18 | 86749520 | 0 | 30100000 | 48049520 | 78149520 | [5 empty] | Locally | Yes
Hampton Roads | stip | project | 127093 | Interstate | Chesapeake | Reconstruction W/ Added Capacity | [5 empty] | I-64/I-464 INTERCHANGE PHASE A | Bainbridge Blvd | Battlefield Blvd | 0464 | I-64/I-464 | 0 | 0.22 |  |  | 7755555 | 11889699 | 119354746 | 139000000 | 139000000 | 2025-12-19 | 2028-07-30 | 2028-07-30 | 2029-12-31 | 2029-12-31 | 2032-06-30 | 109161306 | 7755555 | 11889699 | 0 | 19645254 | 0 | 0 | 0 | 0 |  | VDOT | Yes
Hampton Roads | stip | project | 127600 | Primary | James City County | Facilities For Pedestrians And Bicycles | [5 empty] | RICHMOND ROAD SIDEWALK INFILL SEGMENT 1 | RTE 649 (BUSH SPRINGS RD) | 0.275 MILES E OF RTE 649 (BUSH SPRINGS RD) | 0060 | Richmond Road | 230.51 | 230.79 | 0.2750 | MI | 240509 | 163796 | 952060 | 1356365 | 1356365 | 2028-07-10 | 2030-10-17 | 2030-10-17 | 2031-08-12 | 2031-08-12 | 2032-07-28 | 240509 | 192407 | 0 | 0 | 192407 | [5 empty] | VDOT | No
Hampton Roads | stip | project | 127825 | Urban | Newport News | Traffic Management/Engineering | [5 empty] | CITYWIDE ITS UPGRADES | Various | Various | U000 | Various | 255.62 | 263.04 |  |  | 300000 |  | 1200000 | 1500000 | 1500000 | 2030-10-01 | 2033-02-15 |  |  | 2033-02-15 | 2034-02-01 | 500000 | 240000 | 0 | 0 | 240000 | [5 empty] | Locally | No
Hampton Roads |  |  | 127832 | Public Transportation | Williamsburg Area Transit Authority | Transit | [5 empty] | CRP Electric/Hybrid Expansion Support Vehicle | [8 empty] | 110000 | 0 | 0 | 110000 |  | 2024-08-01: 2025-07-01; 2026-02-28: 2026-06-30 | 110000 | [8 empty] | FO | WATA-DRPT | No
Hampton Roads | stip | project | 127929 | Urban | Virginia Beach | Facilities For Pedestrians And Bicycles | [5 empty] | #SMART26 VIRGINIA BEACH TRAIL PHASE IV | London Bridge Road | N. Birdneck Road | U000 |  | 1.2 | 4.14 | 2.9400 | MI | 2290102 | 2468290 | 19033951 | 23792343 | 23792343 | 2028-01-13 | 2031-06-05 | 2031-06-05 | 2032-04-15 | 2032-04-15 | 2033-11-25 | 23792343 | 2290102 | 0 | 0 | 2290102 | [5 empty] | Locally | No
Hampton Roads |  |  | 127931 | Urban | Isle of Wight County | Reconstruction W/ Added Capacity | [5 empty] | Route 17 Widening Phase 1 Lane Ext at State Route 669 | 1<000 feet north of route 662 - Whippingham Parkway | Route 669 Smiths Neck Roack | 17 |  |  |  | 0.614 | MI | 1922692 | 3217577 | 10772849 | 15913118 |  | 2025-11-13 | 2028-01-26 | 2028-01-26 | 2028-11-14 | 2028-11-14 | 2029-10-31 | 15913118 | [9 empty] | Locality | No
Hampton Roads | stip | project | 127934 | Urban | Isle of Wight County | Reconstruction W/ Added Capacity | [5 empty] | #SMART26 RT 17 WIDENING PHASE 2 | Rte 258 Brewers Neck Blvd | Rte 669 Smiths Neck Rd | 0017 | Route 17 | 43.75 | 44.56 | 0.8100 | MI | 2689465 | 5428608 | 19216191 | 27334264 | 27334264 | 2028-08-01 | 2032-02-05 | 2032-02-05 | 2033-01-11 | 2033-01-11 | 2034-08-23 | 27334264 | 2689465 | 0 | 0 | 2689465 | [5 empty] | VDOT | Yes

## TIP Projects - DRPT Table Data
STIP_ID | Ind | Fund | Phase | Previous | 2027 | 2028 | 2029 | 2030 | Sum of Years | Date Entered | Date updated | Project Title | Recipent | Notes | Validated | PowerAppsId
WAT6001 | 1 | FTA 5339 |  |  | 197 | 122 | 124 | 168 | 611 |  |  | ADP Hardware and Equipment | Williamsburg Area Transit Authority (WATA) |  | NO
WAT6001 | 1 | FTA 5307 |  |  |  | 220 |  |  | 220 |  |  | ADP Hardware and Equipment | Williamsburg Area Transit Authority (WATA) |  | NO
WAT6001 | 1 | State |  |  | 39 | 67 | 25 | 34 | 165 |  |  | ADP Hardware and Equipment | Williamsburg Area Transit Authority (WATA) |  | NO
WAT6001 | 1 | Local |  |  | 10 | 18 | 6 | 8 | 42 |  |  | ADP Hardware and Equipment | Williamsburg Area Transit Authority (WATA) |  | NO
WAT7001 | 1 | FTA 5339 |  |  | 24 |  |  |  | 24 |  |  | ADP Software | Williamsburg Area Transit Authority (WATA) |  | NO
WAT7001 | 1 | State |  |  | 4 |  |  |  | 4 |  |  | ADP Software | Williamsburg Area Transit Authority (WATA) |  | NO
WAT7001 | 1 | Local |  |  | 1 |  |  |  | 1 |  |  | ADP Software | Williamsburg Area Transit Authority (WATA) |  | NO
WAT0001 | 1 | FTA 5307 |  |  | 4049 | 4092 | 4215 | 4342 | 16698 |  |  | Operating Assistance | Williamsburg Area Transit Authority (WATA) |  | NO
WAT0001 | 1 | FTA 5311 |  |  | 590 | 597 | 615 | 633 | 2435 |  |  | Operating Assistance | Williamsburg Area Transit Authority (WATA) |  | NO
WAT0001 | 1 | Other Federal |  |  | 180 | 191 | 197 | 203 | 771 |  |  | Operating Assistance | Williamsburg Area Transit Authority (WATA) |  | NO
WAT0001 | 1 | State |  |  | 2668 | 2697 | 2778 | 2861 | 11004 |  |  | Operating Assistance | Williamsburg Area Transit Authority (WATA) |  | NO
WAT0001 | 1 | Local |  |  | 1662 | 1680 | 1731 | 1782 | 6855 |  |  | Operating Assistance | Williamsburg Area Transit Authority (WATA) |  | NO
WAT0001 | 1 | Revenue |  |  | 1830 | 1859 | 1905 | 1963 | 7557 |  |  | Operating Assistance | Williamsburg Area Transit Authority (WATA) |  | NO
WAT3001 | 1 | FTA 5339 |  |  | 240 |  |  |  | 240 |  |  | Passenger Amenities | Williamsburg Area Transit Authority (WATA) |  | NO
WAT3001 | 1 | State |  |  | 48 |  |  |  | 48 |  |  | Passenger Amenities | Williamsburg Area Transit Authority (WATA) |  | NO
WAT3001 | 1 | Local |  |  | 12 |  |  |  | 12 |  |  | Passenger Amenities | Williamsburg Area Transit Authority (WATA) |  | NO
WAT4001 | 1 | FTA 5339 |  |  |  |  | 2400 |  | 2400 |  |  | Property & Facilities - Construction of Facilities | Williamsburg Area Transit Authority (WATA) |  | NO
WAT4001 | 1 | State |  |  |  |  | 480 |  | 480 |  |  | Property & Facilities - Construction of Facilities | Williamsburg Area Transit Authority (WATA) |  | NO
WAT4001 | 1 | Local |  |  |  |  | 120 |  | 120 |  |  | Property & Facilities - Construction of Facilities | Williamsburg Area Transit Authority (WATA) |  | NO
WAT2001 | 1 | Other Federal |  |  | 1286 |  |  |  | 1286 |  |  | Revenue Vehicles- Expansion | Williamsburg Area Transit Authority (WATA) |  | NO
WAT2001 | 1 | State |  |  | 257 |  |  |  | 257 |  |  | Revenue Vehicles- Expansion | Williamsburg Area Transit Authority (WATA) |  | NO
WAT2001 | 1 | Local |  |  | 64 |  |  |  | 64 |  |  | Revenue Vehicles- Expansion | Williamsburg Area Transit Authority (WATA) |  | NO
WAT1001 | 1 | FTA 5339 |  |  | 702 |  |  |  | 702 |  |  | Revenue Vehicles- Replacement | Williamsburg Area Transit Authority (WATA) |  | NO
WAT1001 | 1 | Other Federal |  |  |  |  | 2065 | 2137 | 4202 |  |  | Revenue Vehicles- Replacement | Williamsburg Area Transit Authority (WATA) |  | NO
WAT1001 | 1 | State |  |  | 141 |  | 413 | 428 | 982 |  |  | Revenue Vehicles- Replacement | Williamsburg Area Transit Authority (WATA) |  | NO
WAT1001 | 1 | Local |  |  | 35 |  | 103 | 106 | 244 |  |  | Revenue Vehicles- Replacement | Williamsburg Area Transit Authority (WATA) |  | NO
WAT5001 | 1 | FTA 5339 |  |  | 220 |  | 295 |  | 515 |  |  | Support Vehicles- Replacement | Williamsburg Area Transit Authority (WATA) |  | NO
WAT5001 | 1 | State |  |  | 45 |  | 59 |  | 104 |  |  | Support Vehicles- Replacement | Williamsburg Area Transit Authority (WATA) |  | NO
WAT5001 | 1 | Local |  |  | 11 |  | 15 |  | 26 |  |  | Support Vehicles- Replacement | Williamsburg Area Transit Authority (WATA) |  | NO
SUF9001 | 1 | FTA 5307 |  |  | 229 |  |  |  | 229 |  |  | Capital Cost of Contracting | Suffolk Transit |  | Yes
SUF9001 | 1 | State |  |  | 101 |  |  |  | 101 |  |  | Capital Cost of Contracting | Suffolk Transit |  | Yes
SUF9001 | 1 | Local |  |  | 437 |  |  |  | 437 |  |  | Capital Cost of Contracting | Suffolk Transit |  | Yes
SUF0001 | 1 | FTA 5307 |  |  | 352 |  |  |  | 352 |  |  | Operating Assistance | Suffolk Transit |  | Yes
SUF0001 | 1 | State |  |  | 350 |  |  |  | 350 |  |  | Operating Assistance | Suffolk Transit |  | Yes
SUF0001 | 1 | Local |  |  | 352 |  |  |  | 352 |  |  | Operating Assistance | Suffolk Transit |  | Yes
SUF1001 | 1 | FTA 5307 |  |  | 352 |  |  |  | 352 |  |  | Revenue Vehicles- Replacement | Suffolk Transit |  | Yes
SUF1001 | 1 | State |  |  | 70 |  |  |  | 70 |  |  | Revenue Vehicles- Replacement | Suffolk Transit |  | Yes
SUF1001 | 1 | Local |  |  | 18 |  |  |  | 18 |  |  | Revenue Vehicles- Replacement | Suffolk Transit |  | Yes
SSS9001 | 1 | FTA 5310 |  |  | 77 | 80 | 82 | 85 | 324 |  |  | Mobility Management and Other Capital | Senior Services of Southeastern Virginia (SSEVA) |  | Yes
SSS9001 | 1 | State |  |  | 15 | 16 | 16 | 17 | 64 |  |  | Mobility Management and Other Capital | Senior Services of Southeastern Virginia (SSEVA) |  | Yes
SSS9001 | 1 | Local |  |  | 4 | 4 | 4 | 4 | 16 |  |  | Mobility Management and Other Capital | Senior Services of Southeastern Virginia (SSEVA) |  | Yes
SSS0001 | 1 | FTA 5310 |  |  | 21 | 22 | 22 | 23 | 88 |  |  | Operating Assistance | Senior Services of Southeastern Virginia (SSEVA) |  | Yes
SSS0001 | 1 | State |  |  | 17 | 17 | 18 | 18 | 70 |  |  | Operating Assistance | Senior Services of Southeastern Virginia (SSEVA) |  | Yes
SSS0001 | 1 | Local |  |  | 4 | 4 | 4 | 4 | 16 |  |  | Operating Assistance | Senior Services of Southeastern Virginia (SSEVA) |  | Yes
PAA9001 | 1 | FTA 5310 |  |  | 287 | 296 | 304 | 314 | 1201 |  |  | Mobility Management and Other Capital | Peninsula Agency on Aging (PAA) |  | Yes
PAA9001 | 1 | State |  |  | 123 | 127 | 130 | 134 | 514 |  |  | Mobility Management and Other Capital | Peninsula Agency on Aging (PAA) |  | Yes
PAA9001 | 1 | Local |  |  | 89 | 92 | 94 | 97 | 372 |  |  | Mobility Management and Other Capital | Peninsula Agency on Aging (PAA) |  | Yes
PAA0001 | 1 | FTA 5310 |  |  | 146 | 150 | 154 | 159 | 609 |  |  | Operating Assistance | Peninsula Agency on Aging (PAA) |  | Yes
PAA0001 | 1 | State |  |  | 97 | 100 | 103 | 106 | 406 |  |  | Operating Assistance | Peninsula Agency on Aging (PAA) |  | Yes
PAA0001 | 1 | Local |  |  | 24 | 25 | 16 | 27 | 92 |  |  | Operating Assistance | Peninsula Agency on Aging (PAA) |  | Yes
HRT6001 | 1 | FTA 5307 |  |  |  |  | 918 | 127 | 1045 |  |  | ADP Hardware and Equipment | Hampton Roads Transit (HRT) |  | Yes
HRT6001 |  | FTA 5339 |  |  |  | 60 |  |  | 60 |  |  | ADP Hardware and Equipment | Hampton Roads Transit (HRT) |  | Yes
HRT6001 | 1 | Local |  |  |  | 9 | 131 | 32 | 172 |  |  | ADP Hardware and Equipment | Hampton Roads Transit (HRT) |  | Yes
HRT7001 | 1 | FTA 5307 |  |  | 616 | 3887 | 2116 | 957 | 7576 |  |  | ADP-Software | Hampton Roads Transit (HRT) |  | Yes
HRT7001 |  | FTA 5337 | [5 empty] | 366 | 366 |  |  | ADP-Software | Hampton Roads Transit (HRT) |  | Yes
HRT7001 | 1 | Local |  |  | 88 | 1364 | 848 | 206 | 2506 |  |  | ADP-Software | Hampton Roads Transit (HRT) |  | Yes
HRT9005 |  | FTA 5307 |  |  | 306 |  |  |  | 306 |  |  | Facility Ugrades | Hampton Roads Transit (HRT) |  | Yes
HRT9005 |  | Local |  |  | 44 |  |  | 45 | 89 |  |  | Facility Ugrades | Hampton Roads Transit (HRT) |  | Yes
HRT9005 |  | RSTP |  |  | 7047 |  |  | 506 | 7553 |  |  | Facility Ugrades | Hampton Roads Transit (HRT) |  | Yes
HRT0001 | 1 | RSTP |  |  | 1600 | 1442 | 1485 | 1530 | 6057 |  |  | HRT TRAFFIX Program | Hampton Roads Transit (HRT) |  | Yes
HRT0001 | 1 | State |  |  | 400 | 411 | 424 | 436 | 1671 |  |  | HRT TRAFFIX Program | Hampton Roads Transit (HRT) |  | Yes
HRT9001 | 1 | FTA 5337 |  |  | 1415 | 3536 | 1213 | 3370 | 9534 |  |  | LRT-State of Good Repair | Hampton Roads Transit (HRT) |  | Yes
HRT9001 | 1 | Local |  |  | 203 | 504 | 894 | 491 | 2092 |  |  | LRT-State of Good Repair | Hampton Roads Transit (HRT) |  | Yes
HRT9001 | 1 | State |  |  | 3437 | 8586 | 88 | 7976 | 20087 |  |  | LRT-State of Good Repair | Hampton Roads Transit (HRT) |  | Yes
HRT2001 | 1 | FTA 5307 |  |  | 546 |  |  |  | 546 |  |  | Revenue Vehicles- Expansion | Hampton Roads Transit (HRT) |  | Yes
HRT2001 | 1 | State |  |  | 1327 |  |  |  | 1327 |  |  | Revenue Vehicles- Expansion | Hampton Roads Transit (HRT) |  | Yes
HRT2001 | 1 | Local |  |  | 78 |  |  |  | 78 |  |  | Revenue Vehicles- Expansion | Hampton Roads Transit (HRT) |  | Yes
HRT1001 | 1 | FTA 5307 |  |  | 84 | 390 | 1599 | 1801 | 3874 |  |  | Revenue Vehicles- Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT1001 | 1 | Local |  |  | 12 | 56 | 3883 | 257 | 4208 |  |  | Revenue Vehicles- Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT1001 | 1 | State |  |  | 204 | 947 | 228 | 4373 | 5752 |  |  | Revenue Vehicles- Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT9002 | 1 | FTA 5307 |  |  | 461 | 291 | 312 | 740 | 1804 |  |  | Safety and Security SGR | Hampton Roads Transit (HRT) |  | Yes
HRT9002 | 1 | Local |  |  | 66 | 90 | 45 | 106 | 307 |  |  | Safety and Security SGR | Hampton Roads Transit (HRT) |  | Yes
HRT9002 | 1 | State |  |  | 1120 | 659 | 758 | 1796 | 4333 |  |  | Safety and Security SGR | Hampton Roads Transit (HRT) |  | Yes
HRT4001 | 1 | FTA 5307 |  |  | 130 | 385 |  |  | 515 |  |  | Transfer Center Upgrades | Hampton Roads Transit (HRT) |  | Yes
HRT4001 | 1 | State |  |  |  | 936 |  |  | 936 |  |  | Transfer Center Upgrades | Hampton Roads Transit (HRT) |  | Yes
HRT4001 | 1 | Local |  |  | 33 | 55 |  |  | 88 |  |  | Transfer Center Upgrades | Hampton Roads Transit (HRT) |  | Yes
HRT3001 | 1 | FTA 5307 |  |  |  | 809 |  |  | 809 |  |  | Passenger Amenities | Hampton Roads Transit (HRT) |  | Yes
HRT3001 | 1 | State |  |  | 211 | 1965 |  | 102 | 2278 |  |  | Passenger Amenities | Hampton Roads Transit (HRT) |  | Yes
HRT3001 | 1 | Local |  |  | 99 | 116 |  | 48 | 263 |  |  | Passenger Amenities | Hampton Roads Transit (HRT) |  | Yes
HRT5001 | 1 | Local |  |  | 56 | 20 | 70 | 56 | 202 |  |  | Support Vehicles- Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT5001 | 1 | State |  |  | 120 | 44 | 148 | 120 | 432 |  |  | Support Vehicles- Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT9003 | 1 | FTA 5307 |  |  |  | 187 | 1848 | 198 | 2233 |  |  | Transit Bus Mid-Life Repower Project | Hampton Roads Transit (HRT) |  | Yes
HRT9003 | 1 | Local |  |  |  | 27 | 264 | 28 | 319 |  |  | Transit Bus Mid-Life Repower Project | Hampton Roads Transit (HRT) |  | Yes
HRT9003 | 1 | State |  |  |  | 454 | 4489 | 492 | 5435 |  |  | Transit Bus Mid-Life Repower Project | Hampton Roads Transit (HRT) |  | Yes
HRT1002 | 1 | State |  |  | 9404 | 17495 | 6527 | 5712 | 39138 |  |  | Transit Bus Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT1002 | 1 | RSTP |  |  | 1953 | 13277 | 9543 | 4587 | 29360 |  |  | Transit Bus Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT1002 |  | Other Federal |  |  |  |  | 2687 | 2352 | 5039 |  |  | Transit Bus Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT1002 |  | FTA 5339 |  |  |  | 4059 |  |  | 4059 |  |  | Transit Bus Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT1002 |  | FTA 5307 |  |  | 3872 | 3145 |  |  | 7017 |  |  | Transit Bus Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT1002 | 1 | CMAQ |  |  | 2000 | 0 | 0 | 4956 | 6956 |  |  | Transit Bus Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT1002 |  | Local |  |  | 553 | 1029 | 384 | 336 | 2302 |  |  | Transit Bus Replacement | Hampton Roads Transit (HRT) |  | Yes
HRT6001 | 1 | State |  |  |  | 146 | 2229 |  | 2375 |  |  | ADP Hardware and Equipment | Hampton Roads Transit (HRT) |  | Yes
HRT7001 | 1 | State |  |  | 1495 | 8307 | 4420 | 2824 | 17046 |  |  | ADP-Software | Hampton Roads Transit (HRT) |  | Yes
HRT9005 |  | State |  |  | 740 |  |  | 574 | 1314 |  |  | Facility Ugrades | Hampton Roads Transit (HRT) |  | Yes
HRT9006 | 1 | FTA 5307 |  |  | 506 |  |  | 506 | 1012 |  |  | Ferry State of Good Repair | Hampton Roads Transit (HRT) |  | Yes
HRT9006 | 1 | State |  |  | 450 |  |  | 575 | 1025 |  |  | Ferry State of Good Repair | Hampton Roads Transit (HRT) |  | Yes
HRT9006 | 1 | Local |  |  | 40 |  |  | 45 | 85 |  |  | Ferry State of Good Repair | Hampton Roads Transit (HRT) |  | Yes
DRPT1005 | 1 | FTA 5310 |  |  | 1301 | 1431 | 1574 | 1731 | 6037 |  |  | Acquisition of Accessible Vehicles | Department of Rail and Public Transportation |  | Yes
DRPT1005 | 1 | State |  |  | 42 | 47 | 51 | 56 | 196 |  |  | Acquisition of Accessible Vehicles | Department of Rail and Public Transportation |  | Yes
DRPT1005 | 1 | Local |  |  | 299 | 329 | 362 | 398 | 1388 |  |  | Acquisition of Accessible Vehicles | Department of Rail and Public Transportation |  | Yes